## 1
1. Partner in the educational mission of the university to develop and inspire students to discover, access, and use information effectively for academic success, intellectual growth, and lifelong learning.
IT Operations | Continue to investigate, promote the use of, and increase the availability of new and emerging teaching and learning technologies in the library including 1) collaborative touch screen technologies in the classrooms and CLC, 2) mobile devices in the classrooms and for internal faculty and staff, and 3) collaborative technologies for student use, such as large screens, laptops, and desktop screen sharing. | Number of technologies investigated; number of technologies adopted or promoted; methods used for promotion; number of items purchased and made available | June 30, 2013. | 10 iPads were deployed to RIS for instructional use in the classrooms. We have acquired 10 additional large screens for the CLC and study rooms for students to use.
IT Operations | Collaborate with ITCS and Public Services to identify and fund technology investment opportunities including additional Apple products and mobile large screens for student use. Investigate the need for multimedia production and seek funding if need is shown. | Number of items purchased; documentation of source of funds. | June 30, 2013. | The remainder of our student computers have been purchased using STF funds. The last round included 53 desktops, as well as 30 additional laptops for Circulation. Of the 53 desktops, 19 were iMacs, and 10 MacBooks pros were purchased through STF. All iMacs include video editing software, and 2 additional Mac Pro desktops were purchased for video editing with Final Cut Pro.
Manuscripts and Rare Books | Update the former Special Collections Department online tutorials to reflect the current organizational structure and services of the Manuscripts and Rare Books Department and the University Archives. By testing them on current student employees, ensure that they are brief, modular in nature, and appealing to students. | At least five tutorials of no more than three minutes in length will be updated and available. During the spring semester, 2013, students who use the tutorials will be asked for feedback in brief surveys. | By December 31, 2012, the tutorials will be updated and available on the departments' Web pages. | It was decided that it was more efficient to produce one comprehensive tutorial. This tutorial will be completed by the 2013 fall semester.
Manuscripts and Rare Books | Organize an orientation session for new and returning students in the Program in Maritime Studies in August 2012 to promote knowledge and use of the holdings of the Manuscripts and Rare Books Department. | At least 50% of the students in the program attend the session. During the academic year, at least two students in the program utilize the holdings of the department for research. | May 15, 2013. | A very successful orientation session was held on August 22, 2012. Nineteen students attended. This represented 100% of beginning students and approximately 60% of new and second-year students. They were exposed to online sources and tools and given tours of the North Carolina Collection and Manuscripts and Rare Books Department. They were most interested in the original manuscript material and rare books shown them in the Manuscripts and Rare Books Department.
Manuscripts and Rare Books | Update the department’s online citation guide to include examples of citations for digital images. Consider using the LibGuide template if appropriate. | Documentation that guide is updated and current. | September 1, 2012. | This goal was accomplished by September 1, 2012. The guide is available on the Web page of the Manuscripts and Rare Books Department: http://www.ecu.edu/cs-lib/spclcoll/citematerial.cfm
Music | Develop a plan for a personal music librarian program for School of Music students and faculty for implementation in the 2013-14 academic year. | Documentation that plan has been developed. | Plan completed by June 2012 and ready for implementation in August 2013. | Completed.
North Carolina Collection | Employ available communication technologies including chat reference to encourage student use of collection. | Implementation of chat reference. | December 15, 2012. | Although programming was set up, implementation was cancelled. Instead, the department will pursue chat reference as part of the implementation of LibAnswers by Public Services and Special Collections in the coming year. The need to present the user with a consistent interface throughout the library was considered more pressing than the immediate implementation of chat reference.
Research and Instruction | Investigate the redesign of the ECU Libraries tab within Blackboard based upon Google Analytics. Also, explore other possible options for integrating LibGuides, tutorials, and/or learning objects within Blackboard. | Documentation of redesign and integration options. | Redesign ECU Libraries tab by August 2012. Explore other options by December 2012. If feasible, implement by June 2013. | Based on use of the library through Google Analytics statistics, the ECU Libraries tab was redesigned in Blackboard to mirror the OneSearch and other options from the libraries' webpage. The new easy-access design was implemented before the beginning of the fall semester. A new instance of the webpage was implemented by Application and Discovery Services prior to the External Program Reviewer's visit. During the fall of 2012, the library was contacted by the Blackboard Administrators about the responses received in one of their faculty surveys about the need for more library resources in Blackboard. After meeting with Bb administrators, the Instructional Design Librarian worked with them to design a module which faculty members can copy into their sites which include resources for their disciplines. Also a student module was created which appears for all students. The modules went live in March 2013.
Research and Instruction | Collaborate with the ECU Passport program, University Writing Center, Office of Student Rights and Responsibilities, and the English Composition faculty to provide at least 5 presentations about avoiding plagiarism; publicize such activities to faculty in the e-newsletter. | Number of presentations; documentation of publicity. | May 2013. | As a response to the teaching faculty's desire for more plagiarism education, RIS taught 1 class as part of the ECU Passport Program which attracted over 20 students, created/updated a handout about academic integrity for the Office of Student Rights and Responsibilities, and continued to incorporate the information into COAD 1000 and ENGL 1100 instruction sessions. Also, the Instructional Design Librarian created several learning objects including citation tutorials, a video, and adapted a plagiarism quiz for use in LibGuides and Blackboard. Also, the Instruction Coordinator and Head of Service met with the Director of the Writing Center and Director of First-Year Writing Program to determine ways to collaborate with them in the future. They saw the library's role as one of reinforcement, not teaching of plagiarism skills as an entire month is spent on plagiarism education in ENGL 1100.
TRC | Develop pilot plan to implement and provide Instant Messaging (IM) as an additional method to request help from the Teaching Resources Center. | Availability of IM service; number of uses; documentation of assessment. | Develop service over summer 2012, implement service for fall 2012 semester, assess service by May 2012. | TRC employees were trained on online-chat/IM procedures in early summer 2012. Practice sessions were provided and completed by all members of the TRC with an August 1st implementation. Chat service was manned by person scheduled at TRC desk. In August, there were 30 chat sessions with an increase to 55 in Sept and Oct. From Nov to present, service has averaged 31 chats per month. While the department is disappointed in the number of sessions, members of the TRC are willing to continue the service. Discussion has been had with the AD of Public Services on combining chat services.
University Archives and Records Management | Update the former Special Collections Department online tutorials to reflect the current organizational structure and services of the Manuscripts and Rare Books Department and the University Archives. | Number of tutorials that are updated and available on the website. | December 31, 2012. | Tutorial content updated by end of December but design is basic. Tutorial is in the process of being designed by Application Services and Design and will be available by September 2013.
University Archives and Records Management | Form a relationship with a department or professor that results in the use of University Archives materials. Discuss possibilities for partnerships with African and African American Studies, the Urban and Regional Planning Program, and with the University Historian to increase use of collections by students by the end of 2012. | Number of discussions held regarding possible partnerships. | December 31, 2012. | Met with representatives from all three areas and have plans in place with the University Historian and with African and African American Studies.
Note on A1: Insert progress report in the Outcome column -Mark Sanders

## 2
2. Assess physical and virtual library spaces and make short-term improvements as well as long-term plans that will support the research and learning needs of all user groups, promote the discovery and production of knowledge, and make efficient use of resources.
Application Services and Design | Continue to evaluate effectiveness of website by reviewing analytics and conducting usability studies. | Implement changes to website based on user feedback and patterns discovered in analytics. Solicit user feedback, research search strategies at other libraries, review other products in the market (done in conjunction with Discovery Committee and Discovery Services dept.) | Ongoing. | Review of analytics is on-going as is better organization of analytics gathering to better inform on future direction. To date no usability studies have been conducted, though there are plans to evaluate web pages and custom applications in FY2013-2014.
Application Services and Design | Consolidate fragmented search interfaces in the short-term by consolidating search widget tabs into a single search box and in the long-term by building a new search interface using APIs to offer users results from multiple repositories with one search. | User feedback; environmental scan of search strategies at other libraries; review of other products in the market (in collaboration with Discovery/Search Committee and Discovery Services Department. | Search widget tab consolidation: August 30, 2012; environmental scan and product review: June 30, 2013; new search interface: no date set yet. | Done. A new widget was deployed to all of the library's home pages that simplified the search to one prominent box. Links to additional resources were consolidated below the search. A custom page is under development that uses APIs to personalize and structure search results.
Building Ops/Circulation/ILL | Participate in the remodel of the Circulation, Interlibrary Loan, and Security work areas and the relocation of the Coffee Shop. | With AD for Public Services, architects, ECU Facilities, and relevant departments, final space plans are completed and implementation started for remodel to combine Circulation and Interlibrary Loan, install coffee shop in new location, and renovate first floor entrance area. Final space plans are completed and implementation started for 24-hour study space. Assess functionality of new space and associated equipment and furnishings and make changes in workflow or configurations to maximize staff satisfaction and efficiency. | Final space plans completed by March 30, 2013. Construction is currently scheduled to begin in May 2013 and continue for approximately 3 months. Assessment activities will occur in 2013-2014 year. | The final plans were decided on between Circulation and Interlibrary Loan departments; the plans include location of each department's work/processing spaces, staff offices and cubicles, shelving, and storage. Temporary office spaces were identified and plans were made for the moves. Departments moved into temporary spaces in April and May. Renovation began in May with an expected occupancy in August 2013.
Business Operations | Plan the efficient and timely expenditure of monies allocated from the operating budget, endowment distributions, special funds, and other sources for physical renovations and associated technology and equipment so that the appropriate funding source is used and all conditions for use are met. | Deadlines for submitting requests to Division of Academic Affairs or other funding sources are met; deadlines for spending monies from these sources are met; operating budget allocations for physical renovations and associated technology and equipment are encumbered and/or expended by April 15, 2013; a minimal number of items have to be recoded. | April 15, 2013 for operating budget; June 15, 2013 for recoding; all external deadlines are met. | All deadlines were met. Due to a change in rules regarding the use of lapsed faculty salaries, student payroll expenses for several pay periods had to be recoded. Otherwise, recoding was minimal.
Circulation | Promote usage of self checkout machine with frequent staffing to assist patrons in the machine's operation. | Statistics for self-checkout machine comprise 5% of total circulation. | December 31, 2012. | During the report period, 2,820 patrons used the self-checkout machine to discharge 5,015 items.
Discovery/Search Committee | Work with the Single E-Library and E-Resource Usability Task Forces to implement improvements and a more unified discovery experience for ECU patrons. | Relevant changes made to discovery interfaces per work of groups; input given. | Dependent on work of task forces; E-library task force goal is to have a Single E-library instance available by beginning of fall semester 2012. | The single e-Library task force successfully developed and implemented a single online catalog for all of the ECU Libraries. This was not simply folding one instance into another, but a total rebuild of the online catalog which included steps to consolidate services and improve the overall interface. Consolidated efforts stemming from this project include a single purchase request mechanism, a consolidated interface for access to the ECU Libraries Interlibrary Loans, implementation of recall request at both libraries including a courier service to transport materials between the two libraries, a consolidated course reserves page, Ask a Librarian routing service, and a single, customized combined instance of WorldCat Local. This single instance of the catalog became the default catalog that functions along side our Summon discovery service. Projects initiated and implemented on behalf of the e-Resources usability task force include a combined ECU Libraries landing page which is duplicated from the ECU Libraries tab within Blackboard and from the Libraries link at the ECU website level. This group also developed a single search widget to operate across the libraries to create a seamless search experience. Projects currently underway include creation of a single, combined Databases List, a universal Research Guides (LibGuides) landing page, and customization of the Serials Solutions 360 link page. Projects not yet underway, but in the very beginning stages of development include a single, custom search results page, a rotating shelf browse application, and a VuFind discovery layer for the e-Library OPAC.
Discovery/Search Committee | Continue to investigate new and current discovery tools. In particular, evaluate Summon and keep abreast of developments in OCLC Worldshare and Serials Solutions Intota web-scale products. Keep a pulse on ECU's overall discovery environment. | Decision regarding Summon review made; review conducted if necessary; members read, attend in-person and virtual sessions, share information gathered with libraries and take appropriate actions. | Decision by end of 2012 on whether it is necessary to conduct a thorough review of Summon. (Current Summon subscription expires in Aug. 2013.) | At the end of CY2012 the Discovery Committee decided against a formal review of other discovery systems at present, and suggested renewal of Summon for the 2012-2013 fiscal year. The rationale stemmed from the ECU Libraries being heavily invested in other Serials Solutions products and a change in our discovery tool to a different vendor would radically impact other e-resource management tools and would require a thorough evaluation of workflow processes. Members of the committee, including the Discovery Services Librarian actively participate in professional development opportunities to learn about other discovery tools and library management systems on the market. Members have participated in on site presentations of OCLC's WorldShare, met with vendors at national conferences to discuss and demo other systems such as SS's Intota, and participated in numerous webinars and online conference opportunities to learn more about the evolving discovery marketplace. The committee has also provided recommendations where appropriate such as the recommendation to explore and implement the VuFind open source discovery layer as a catalog replacement for e-Library.
Discovery/Search Committee | Continue to monitor and compare use statistics for Summon, E-library, WorldCat Local, and library website. Develop framework for statistic gathering, including what statistics to gather and methods of analysis and evaluation. | Framework developed and appropriate statistics identified, gathered, and analyzed; decisions made based on statistics. | Framework developed by September 2012. | In the fall of 2012 the Discovery Committee developed a statistics framework for gathering and reporting out use statistics from our primary discovery tools including Summon One Search, the e-Library OPAC, WorldCat Local, and the Library Website. This included specification of specific stats to gather, tools to be utilized for collection, and primary responders for data reporting. It was determined by the committee that it would be the primary responsibility of the Discovery Services Librarian to gather and report out these statistics to the ECU Libraries at the conclusion of fall and spring semester. In addition, the Discovery Services Librarian will be working with Application Services and Design to implement this framework into the larger statistics dashboard that is being developed in collaboration with ECU's ITCS department.
Discovery Services | Participate in the assessment of library implementations of WorldCat Local, Symphony OPAC, and the discovery tool for finding various types of locally-held materials; support the activities of the Discovery/Search, Symphony OPAC, and Single eLibrary committees; provide feedback and/or data to the group(s) that conduct(s) this assessment. | Timely participation in the assessment process and implementation of desired changes and enhancements to the discovery interface resulting from the assessment. | Ongoing. | It is an annual goal of the Discovery Committee to provide a report on a bi-annual basis detailing use statistics from the Libraries' suite of discovery tools. It is also a goal of the Discovery Services Librarian to conduct a formal usability study during FY2013-14 to guide decision making for future initiatives. The Symphony OPAC committee and single e-Library taskforce, including their individual charges and assignments, have since been absorbed into the Discovery Committee. The work of the Discovery Committee with the inclusion of these two groups has been supported in numerous ways by ILS/Discovery Services staff including implementation of the single e-Library OPAC and general record load maintenance as it pertains to the Symphony database and Summon One Search.
Discovery Services | Continue to research and investigate new products and services in the Integrated Library Systems and Discovery Tool markets and compare longer-term viability of current applications; provide and/or promote opportunities such as webinars, articles, or meetings to library faculty and staff to learn about new features and systems available in the ILS and Discovery Tool marketplace; conduct discussions in either a library forum or "brown bag" format for library faculty and staff to discuss new services and systems that have been observed in the ILS and Discovery Tool marketplace. | Narrative in the department's annual report documenting research and investigation; at least three events and two discussion sessions are held. | June 30, 2013. | Members of the Discovery Committee, which includes members of the ILS/Discovery Services department, actively participate in professional development opportunities to learn about other discovery tools and library management systems on the market. Members have participated in on site presentations of OCLC's WorldShare, hosted online webinars and panel discussions regarding implementation of Ex Libris' Alma Library Management System, and the Kuali Foundation's Open Library Environment project. The Discovery Services Librarian in August of 2012 gave a presentation to the ECU Libraries providing updates and an annual review of Discovery Services and Summon One Search. An update of this presentation will be offered again at the close of the academic year.
Discovery Services | Continue to improve the functionality and usability of the Symphony OPAC by identifying and implementing features that mesh into the overall vision and plan for the OPAC and by downloading and reviewing the Web Services and Bookmyne products and consulting with Application Services & Design concerning possible implementation or incorporation into current mobile applications. | Documentation of enhancements and modifications implemented. For desired features not readily available, documentation of submission of enhancement requests to the vendor and/or identification of other means of accomplishing the desired feature. | June 30, 2013. | The single e-Library OPAC for the ECU Libraries was completed in August of 2012. The Libraries assembled a task force of individuals with representation from all libraries. The task force was able to implement features to enhance the catalog interface and streamline shared services. A separate task force conducted an evaluation of e-Library indexing to determine if tweaking the index would result in better result relevancy. The determination of the group was that no further additions or retractions to the index would improve the effectiveness of the search. The Discovery Committee acted on this data to support a recommendation to investigate a suitable catalog replacement, specifically the VuFind discovery layer. The ILS Administrator documented workflows and processes throughout the process.
Electronic & Continuing Resources Acquisitions | Enhance the Joyner Current Periodicals (JCP) shelving area to make more efficient use of space and facilitate patron browsing. | All issues of titles that are no longer subscribed to in print are removed from JCP within 6 months of the date that the last subscribed-to issue was received in print. Processing backlogs do not occur that would result in title issues not fitting in their allotted shelving space. All titles shelved in JCP are clearly and accurately labeled. Titles shelved in JCP are shifted at least once annually to make more efficient and convenient use of space. | Ongoing, as there are changes in the titles and issues shelved in JCP. | This is an ongoing goal that is currently being met.
ILL | Migrate department webpages and revise content and tutorial videos for currency and usability. | Documentation of migration of webpages and revision of tutorials. | Content is migrated and revised by June 2013. | All webpage content was reviewed and updated and webpages were migrated to the library's current template in fall 2012. 22 entries were written for the new Public Services FAQ tool in April. Tutorials were reviewed, but not replaced due to two extended staff vacancies.
ILL | Revise ILLiad interface in response to user feedback, service changes, and system enhancements. | Documentation of revisions made. | Interface is revised by June 2013. | A single Joyner/Laupus ILLiad login page was created to which shared search tools now direct patrons. The Joyner/Laupus ILLiad databases were merged, necessitating mainly behind-the-scenes changes to the patron web interface and the creation of a shared new user registration page. Two ILLiad upgrades were applied that will allow additional enhancements. Due to two prolonged staff vacancies, further enhancements were not made.
IT Operations | Investigate, invest in, and implement infrastructure and equipment to support the growth and changing needs of the library: 1) replace aging infrastructure such as projection systems, computer workstations and laptops, 2) identify spaces in the library that are suitable for collaborative technology implementations and invest in those technologies, 3) promote the use of teaching and learning technologies in the library to campus faculty through demonstrations and tech tours, 4) renovate room 1415 for classroom and student use, with collaborative and interactive technologies. | Documentation of equipment purchased and installed, infrastructure improvements made, spaces identified, and contacts made with faculty. | 1) March 31, 2013; 2) ongoing; 3) June 30, 2013; 4) June 30, 2013 | 56 new laptops were purchased to replace aging departmental, staff, and faculty workstations. 40 desktop computers were purchased to replace aging faculty and staff desktop workstations, and 60 workstations were purchased to replace aging student employee and departmental workstations. Due to new construction and space constraints, as well as internal organizational changes, we have not made many improvements in the area of collaborative technologies for students. Room 1415 has not been modified yet, as it may be converted to a BI classroom.
IT Operations | Carry out plans to utilize room 1418 as a dual library instruction classroom and Technology Commons. | Room ready for use. | January 7, 2013. | This project was put on hold due to delays in construction. Will continue later this semester and into the summer.
Manuscripts and Rare Books | Update the Web pages of the Manuscripts and Rare Books Department to comply with new templates. Explore with Web services the feasibility of including rotating images of departmental holdings on homepage, with a view toward implementing this feature during the 2013-2014 academic year if it is deemed appropriate. | Number/percent of Web pages updated; documentation of investigation of rotating images feature. | Web pages are updated by August 15, 2012. Rotating images feature implemented by May 31, 2014, if deemed feasible. | The Web pages of the department were updated by August 15, 2012. The department decided that rotating images were not feasible for use on the homepage.
Music | Complete development of response plan to the 2011 patron activity study. With the assistance of an outside consultant, develop several remodeling concepts incorporating recommendations from the patron activity study response plan with an eye to increasing the size of the music library. | Response plan developed; remodeling concepts completed. | December 31, 2012 for the response plan; June 30, 2013 for the remodeling concepts. | Response plan completed, and two meetings with the architect completed (the first to examine the space, and the second to review 3 possible scenarios with Music Library and School of Music staff).
Research and Instruction | Evaluate results of Reference Workspace Inventory from respondents on the first floor of the Department. Assess the basement work area with same inventory and create list of short-term improvements. | Documentation of evaluation and assessment; creation of list. | Workspace inventory analyzed by August 30, 2012. Basement assessed by December 31, 2012. Short-term improvements for both areas implemented by June 30, 2013. | Workspace inventory completed and all short-term improvements have already been implemented. Changes included moving staff into new offices, adding student employee lockers, providing larger monitors to some staff members based on work needs, and creating a meeting area for the department which is now located in room 1109.
Research and Instruction | Develop a design plan for room 1418 to serve as an instruction classroom and as part of the Collaborative Learning Center at other times. | Plan developed and design implemented. | Room ready for use by January 7, 2013. | Action on this goal was delayed. Had to await information and budgeting information from ECU Facilities. Planning was completed in Spring 2013 and expected completion of the room is now set for August 2013.
Research and Instruction | Collaborate with the Office of Faculty Excellence and the University Writing Program to negotiate use of library space and increase library-related collaborations with the department. | Documentation of discussions and plans. | Initial completion December 1, 2012; ongoing as needed in 2013. | The Head of RIS and AD for Public Services communicated regularly with the Directors of the Writing Center and the Office of Faculty Excellence to ensure sufficient space was allocated in the library for their needs until they are able to move into their new area. The Instructional Design Librarian collaborated with the OFE to present information about RefWorks, library services, and instructional design techniques for the Teaching with Technology workshop and the Introduction to College Teaching workshop.
Security | New Security Desk is designed and installed. Security collaborates as needed with architect, ECU Facilities and Building Operations during design and construction phases to achieve turnkey product. | New desk is installed; configuration is reviewed and revised as necessary. | June 30, 2013. | Desk was designed and installed on time. Awaiting review of configuration.
TRC | Using the Betty Debnam Hunt Endowment Fund Agreement, develop a plan that will support the Betty Debnam Hunt Instructional Room based upon listed purposes and uses of funds. | Plan developed; materials purchased. | Establish funding and considerations for prioritized purchase(s) by Nov. 2012. Purchase materials by June 2013. | Funds were provided to TRC in the amount of $4,000.00 from library administration (July 2012). $1,700.90 was spent on the Betty Debnam Hunt Technology Classroom dedication plaque leaving a balance of $1,299.10 to be used on purchasing resources for the classroom. The HOS of the TRC and Joyner IT collaborated to add one monitor with laptop hook up capability to the room for patrons to use during study sessions. Consideration to make the classroom a simulated classroom presentation room for teacher education students has been discussed as a possible option at a later date. Funding for the endowed classroom will not be available for at least two years. This goal will be revisited at that time when money is available.
TRC | Using data results from the TRC renovation assessment tools gathered during 2011-2012, develop a list of recommendations regarding TRC space and collections to present for discussion to library administration for consideration. | Plan submitted to library administration. | Present recommendations to the library administration by September 2012. Implement approved recommendations by June 2013. | Summary of results from the TRC renovation assessment was compiled and distributed to members of the TRC and the AD for Public Services by July 31, 2012. Members of TRC met on Aug 3, 2012 to develop a list of recommendations based on the assessment results. A list of sixteen TRC Recommendations for Consideration, ranked in priority order, was finalized on Aug 26, 2012. The list was shared with the Interim Dean and AD for Public Services. Discussion with AD for Public Services was conducted in Sept 2012. Four of top ranked recommendations were immediately addressed and completed: 1)TRC Service Desk hours were extended to 11:00 pm Sun-Thurs, 2) TRC resources continue to be purchased based upon funding, 3) new book displays were purchased, and 4) "L" section in TRC is being reviewed with relocation of some materials to provide additional spacing for TRC collection expansion and the addition of more student study areas Review project was completed in Apr 2013 with shifting by Circulation to be completed by June 2013. Recommendations for additional renovations to this area will be discussed in summer 2013 with a new goal to be in place for 2013-2014.
University Archives and Records Management | Update the departments' webpages to comply with new templates. | Evidence that all webpages have been updated. | August 15, 2012. | Webpages updated by October 15, 2012 after delay in receiving templates from Application and Discovery Services department. Content for Records Management pages completely rewritten and updated to reflect new workflows by June 2013.

## 3
3. Define and communicate the ECU Libraries’ role in supporting the creation, discovery, sharing and preservation of the University’s scholarship, history and academic accomplishments.
Collection Development | Collection Development Librarians will support the Digital Scholarship pilot projects on an as needed basis. | Narrative in the department's annual report to address issues such as how librarians add value and how satisfied our partners are. | June 30, 2013. | The Coastal Atlas project has continued, with the server arriving and being installed, a very nice front page designed, and a bibliography under development.
Collection Development | Collection Development Librarians will support scholarly communication endeavors, including The ScholarShip and any initiatives developed by the Scholarly Communications Committee. | Narrative in the department's annual report. | June 30, 2013. | Ongoing efforts include Dept. meetings, campus wide meetings on author rights, evaluating publishers, data management plans, data repositories and meetings with journal editors; a temp person was hired to help with various projects
Manuscripts and Rare Books | Depending upon whether Joyner Library consolidates all social media initiatives or allows departments to maintain them, add images and appropriate metadata from previous exhibits to a Flickr site; ensure that the library retains ownership to the images. | Number of images added to Flickr site; number of exhibits reflected; documentation of copyright ownership of images; number of views. | June 30, 2013. | The division-wide social media committee chose to focus on Facebook for the 2012-2013 academic year. The department is continuing to look at the feasibility of creating a departmental account and adding images to Flickr. Staff will decide on the project by the 2013 fall semester.
Manuscripts and Rare Books | Add a component to the Web pages of the Manuscripts and Rare Books Department explaining the work of the conservation lab in preserving and making available unique primary sources. | Creation and public availability of this information on website. | Web page is created and linked to departmental page by March 30, 2013. | Due to organizational changes, staff members moved the deadline up June 30, 2013. The page was completed in mid-June 2013.
Music | Create complementary music library collection and donor web pages to highlight collections, honor those who made them possible, and encourage future donations. | Documentation of creation of web pages. | Web pages completed and live by June 30, 2013. | Collection pages developed.
North Carolina Collection | With Digital Collections, complete the quality control of text files for the ECU yearbooks. | Documentation that updated text files for all digitized yearbooks are mounted. | June 30, 2013. | Project was completed ahead of schedule. Editing has been completed on all yearbooks and the text files have all been mounted.
Scholarly Communications | Committee members will help grow The Scholarship @ ECU by providing publicity materials and coordinating outreach efforts on campus. | At least one new collection deposited to The ScholarShip | June 30, 2013. | We have added the first group of Honors Scholars Theses and have created new collections for conference presentations, but have not digitized any print collection.
Scholarly Communications | Plan and promote at least 2 activities on various scholarly communication topics, including for instance, author’s rights, publishing alternatives, and open access to research | Descriptions of activities and total numbers of attendees (if in-person) or online measures (site visits, comments, etc., if online) | June 30, 2013. | Several significant events have been held: in March 2012 there was a forum on faculty authors and journal publication; in October 2012 there was a forum for the Technology Systems Department focusing on evaluating publishers, followed by a general faculty forum on the same topic on February 5, 2013, and another was held in Laupus Library on February 21, 2013.
Scholarly Communications | Determine how best the SCC can support the Digital Scholarship Proposal |  | June 30, 2013. | Committee has been informed about the developments related to the Coastal Atlas, but committee members have not needed to take any action yet.
Scholarly Communications | The Committee will consider the roles of the committee vis-à-vis individual responsibilities | Discussion may lead if prudent to a request for position | December 31, 2013. | A temporary SPA position was hired in March 2013; this person has been working on specific projects related to the Institutional repository, OJS, the Open Journal System software, and Scholarly Communications webpages.
Special Collections Cataloging | Catalog each semester's batch of ETDs in The Scholarship | ETDs cataloged | Before the next batch is delivered | Completed on time.
Special Collections Cataloging | Participate in discussions of changes to The ScholarShip that affect metadata. | Participate as needed | Ongoing | Appropriate members of the department met with Justin Warren, temporary staff member in Collection Development, to discuss ScholarShip metadata. Patricia worked with Joseph Thomas on the appropriate way to add honors college output and undergraduate student papers. Discussions have begun about Dataverse and metadata needs for data curation.
Special Collections Cataloging | Clean up duplication and errors in browse lists in The ScholarShip | Lists examined | Annually, by June 30, 2013 | Completed on time but the work is never really finished.
University Archives and Records Management | Expand electronic record intake program beyond test departments and beyond publications to include all permanent records. | Availability of online training in electronic records by December 2012; University Archives receives electronic records from 20 offices or departments by June 30, 2013. | December 31, 2012 for availability of online training; June 30, 2013 for receipt of electronic records. | Online training has been developed. Working with ASD Department and Digital Archivist to improve intake method.

## 4
4. Responsibly manage, develop and preserve physical and digital collections that support the evolving curricular and research needs of the University.
Administrative Services | Work with the University Archivist to ensure that print and digital administrative records are preserved in compliance with federal and state statutes, university policies and procedures, and library / archives guidelines and best practices. | Assessment Method: Review by University Archivist. Criteria for Success: Positive feedback from University Archivist. | Completed by January 1, 2013. | Three copies of all print marketing materials were sent to Archives. Personnel files are sent on a regular basis in accordance with the records retention schedule. Friends of the Library materials are currently retained on the Pirate drive (General). Met with Arthur Carlson to review departmental compliances.
Application Services and Design | Continue to add enhancements to the Digital Collections public interface. Research Digital Collections interfaces at other libraries and consult literature for new developments. | Enhancements to the interface are released and publicized throughout the year as needed; documentation of enhancements made. | Ongoing. | Completed updates to folder and aggregate objects; JPEG2000 viewer enhancements; archives timeline; began development of crowdsourcing project; began planning for a 'My Collections' feature.
Application Services and Design | Evaluate the effectiveness and relevance of current (legacy) library technology systems/applications and replace with superior and/or more contemporary systems/applications where appropriate. Consolidate existing systems and/or implement new systems while retiring outdated systems and applications. Emphasis will be placed on open-source applications. Examples include Solr and Fedora for use in digital collections repository. | Number of systems/applications evaluated; number of systems/applications replaced; number of systems consolidated; number of systems retired; number of open-source applications implemented. | June 30, 2014. | Room reservation; FAQ system; VisualSVN server; Die-cut search; VuFind; ECU Libraries page. Solr is currently being implemented for the Digital Collections and Institutional Repository. The DSpace repository software has been fully upgraded.
Business Operations | If ALS receives the LSTA grant to expand the Roberts Collection, other grants, and/or acquires the papers of Robert Lee Humber, Business Operations will provide budget support to comply with all grant and project tracking requirements, including tracking grant matches and salaries/wages paid to project archivists and student workers. | Activity codes setup; grant funds tracked. | June 30, 2013. | The LSTA grant to expand the Roberts Collection was received. ALS's match was made from the operating budget and was transferred to the Acquisitions budget and tracked via use of the ProCard. It was not necessary to set up an activity code.
Collection Development | Evaluate, prioritize, and select print and electronic materials in support of the University's research and curricular needs. | Firm order funds expended in a timely fashion. | Ongoing, within target dates for firm order expenditures. | Acquisitions budget ended up overspent for Fiscal Year 2013, not the fault of subject area firm orders, which were placed in a timely fashion. Operating funds and end-of-year funds from Academic Affairs were used to cover the overages.
Collection Development | Scale up to PDA e-book profile to increase the total number of books offered on this plan. | Profile expanded so that the number of records added during the fiscal year is at least 200% above number added during previous fiscal year. | June, 30 2013. | Profile expanded fall semester 2012.
Collection Development | Responsibly deselect materials, primarily federal documents and bound journal volumes to which we have perpetual online access. | Number of items withdrawn. | June, 30 2013. | Deselection project in the L's (with College of Education faculty involvement); Federal Documents deselection from Commerce documents; bound journals, and uncataloged microforms deselected.
Collection Development | Partner with other units to develop a print DDA pilot project. | Print DDA profile submitted to YBP. | September 30, 2012. | Pilot launched Jan. 2013 and is ongoing.
Digital Collections | Continue development of a Fedora based digital repository of institutional materials and digital collections. Create content models and convert administrative forms and request forms to use Fedora's storage model. Create migration plan to be instituted in 2013-2014. | Documentation that content models are created, forms converted, and plan created. | June 30, 2013. | The Fedora implementation plan has been abandoned in lieu of the implementation of SOLR. This project has been progressing on schedule and should be fully operational by early 2014. Until that time, Digital Collections will be providing development assistance and user testing.
Digital Collections | Based on priorities established in the 2010-11 academic year, continue the digitization of manuscript collections and record groups. | At least one new collection identified as having top priority is completed. | June 30, 2013. | Significant progress was made toward the completion of the following for the reporting period: Barbour Boat Works (#758), Joyner (#345), Sparrow (#1).
Digital Collections | Migrate or re-digitize University Archives photo database for inclusion in repository. | Number of images ingested and available. | May 2013. | This goal was completed in December, 2012.
Digital Collections | Develop guidelines for use of newly acquired audio digitization workstation and complete pilot project focusing on an oral history collection. | i) Work station is set up and guidelines for use are developed; ii) pilot project is developed and completed to digitize an oral history collection. | i) December 2012; ii) June 2013. | i) Guidelines have been developed but workstation is still not fully operational due to technical difficulties. Work will begin on pilot project by 8/2013. Ii) Pilot project has been selected and work towards its completion will begin by the date stated above.
Digital Collections | Complete conversion of the access images in the Daily Reflector Image Collection to the JPEG2000 standard to provide access to higher quality files online. Maintain workflow based on the ENCDL migration for derivative creation and access. | All derivatives are available. | December 31, 2012. | This goal was completed in May, 2013.
Digital Collections | Complete trailing projects in the Digital Collections request queue. Evaluate trailing projects in the queue for nearness to completion and develop plan to finish them. | i) Evaluation made and completion plan developed; ii) queue cleared of all trailing projects submitted before January 2012. | i) September 2012; ii) May 2013. | i) Plan was developed in Fall 2012. ii) With the exception of a few trailing projects which will require extra planning and work to complete, this goal has been met.
Digital Collections | Enhance the content and functionality of the University Timeline with input from the faculty and staff of University Archives. Add text written by University Archives to help further contextualize items displayed. Add text timeline developed by University Archivist. | Text and timeline are added. | December 31, 2013. | This goal was completed. Additional text has been added and the Timeline has been expanded to include items from the recently ingested University Archives Photo Database.
Digital Collections | Form a Digital Collections Advisory Committee to assist with prioritization of future projects. | Input is received from University Archives, Special Collections, North Carolina Collection, and Joyner Administration; charge is developed; committee is formed; first meeting is held. | December 2012. | This goal was completed. The first meeting was held in 2/2013 and the call for proposals was distributed shortly thereafter. A total of eight projects were approved in 6/2013 and work has begun toward their completion.
Disaster Preparedness Committee | Review collections disaster plan and update key personnel contact information in the Collections Disaster Plan. | Confirmation of accurate phone numbers by personnel. | Complete by September 1, 2012. | This was completed within the year, but then the committee agreed that since the information is constantly changing, we would change the cycle for updating to quarterly. Also, instead of including this kind of changeable information within the plan itself, we created an emergency contact list of all personnel that is a separate document that is provided to all DEC members. Heads of Service keep emergency contact information on their direct reports and student supervisors keep same for the students they employ. For next year: Document similar information for all other tenants in the building
Disaster Preparedness Committee | Improve awareness of disaster recovery vendor services by scheduling a presentation of services from at least two disaster recovery vendors during the fall 2012 semester. Invite members of the Disaster Preparedness Committee, Disaster Recovery Team, and the Executive Committee to attend. | Plus/delta on presentations by Disaster Preparedness Committee. | Complete by January 1, 2013. | Not completed; will reassess whether the committee should do this next cycle.
Disaster Preparedness Committee | Conduct a disaster drill involving collections to assess the readiness of the Disaster Response Team. | Joint plus/delta with members of the Disaster Preparedness Committee and Disaster Response Team. | Complete by May 1, 2013. | This was not done. Suggestion is to devise a series of tabletop exercises in order to achieve this goal. Will add this as a goal for next cycle.
E-Resources Review Committee | Evaluate and prioritize electronic resources in order to make recommendations of resource acquisition, renewal, and cancellation that support the university's research and curricular needs. | Ongoing input from faculty, students, and ECU Libraries personnel; Lists of added and canceled resources | Ongoing, with meetings approximately monthly. | Achieved. ERRC recommended 24 new acquisitions, 5 cancellations, and 4 changes in concurrent user levels. Additionally, ERRC maintained a 'wish-list' of new acquisitions to pursue pending available funding.
Electronic & Continuing Resources Acquisitions | Carry out electronic and continuing resource orders, licensing, renewals, cancellations, and format and vendor changes in accordance with the decisions of the Electronic Resources Review Committee and of colleagues with collection development decision-making responsibilities. | Orders are placed within 3 working days following decisions to acquire new resources. All necessary license documents are reviewed, negotiated for acceptability, executed, and filed. There are no disruptions in access due to late/unprocessed renewals. Cancellations and format changes are communicated to vendors such that these subscription changes can be made in accordance with the planned effective dates. | Ongoing, as decisions are made about orders, renewals, cancellations, and format changes. | This is an ongoing goal that is currently being met.
Electronic & Continuing Resources Acquisitions | With colleagues at the Laupus Health Sciences Library, assess the effectiveness and return-on-investment of the ECU libraries' current subscription to 360 Resource Manager and investigate if there is another electronic resource management system that would be more effective and/or would yield a higher return-on-investment. | Based on the assessment and investigation, a recommendation is submitted to library administration either to renew 360 Resource Manager or migrate to another electronic resource management system. | Recommendation is submitted by April 30, 2013 (Formerly, timeline for submission was by March 31, 2013. The timeline was revised in April 2013.) | Achieved. Assessment was completed and a recommendation was submitted to library administration to cancel 360 Resource Manager and instead implement CORAL.
Electronic & Continuing Resources Acquisitions | Ensure receipt of subscribed print journals through the check-in and claiming of these materials | Subscribed print journals are checked in within 2 working days of receipt by the library. Unreceived issues of subscribed print journals are identified and claimed. | Ongoing | This is an ongoing goal that is currently being met.
Electronic & Continuing Resources Acquisitions | Develop guidelines that the department can use when reviewing/negotiating license documents for electronic resources. | Guidelines drafted, approved by library administration, and implemented. | Implementation by December 31, 2012. | Achieved.
Manuscripts and Rare Books | The department will endeavor to acquire the papers of Robert Lee Humber. | A contract is signed during the fall of 2012 for the acquisition of the Robert Lee Humber papers. | November 30, 2012. | Mr. Humber met in November 2012 with the head of the Manuscripts and Rare Books Department and with a representative of the ECU Foundation. In that meeting and in a follow-up e-mail message, Mr. Humber agreed to make a bequest of the papers to East Carolina University. He stated his intention to have his attorney develop a codicil to his will to effect this, and agreed to sign the appropriate planned gift form used by the ECU Foundation. Mr. Humber met with Maury York, Jan Lewis, and a representative of the ECU Foundation on April 12, 2013, and presented a letter stating his intention to make a bequest of his family papers. The letter has been placed in a folder in the Contact File ("Humber Papers").
Manuscripts and Rare Books | Conduct and transcribe 5 interviews with African Americans involved in the urban renewal project carried out in Greenville during the 1960s and 1970s. Add the transcribed interviews to the Guides interface and to the Digital Collections repository. Consider the feasibility of planning a digital project in the future that would include photographs, maps, and plans related to urban renewal in Greenville. | Number of interviews conducted and transcribed; availability online; submission of digital projects proposal. | Five persons are identified and have agreed to serve as interviewees by November 1. 2012. The interviews are conducted, transcribed, and made available online by June 30, 2013. A proposal for the digital project is drafted by the same date and submitted to the library committee responsible for prioritizing digital projects. | In December 2012, the department head made contact with Calvin Henderson, head of the Pitt County chapter of the NAACP, who expressed interest in the project. Mr. Henderson agreed to contact a number of citizens in the African American community to encourage them to participate in the project. No further contact has been made. Staff have discussed the importance of contacting Lucille Gorham, who worked for the Redevelopment Commission, to ask her to participate in an interview. Update: Staff has still not heard any definitive plans from Mr. Henderson. An interview with Lucille Gorham is planned for the coming year.
Monograph Acq & P/C | Implement a pilot project for the acquisition of title-by-title firm order streaming media. Identifying departmental responsibilities, establishing a communication routine, responding to technical challenges, and ensuring accessibility are pieces of the workflow to be tested and refined. | Streaming media titles are added to the collection. Move beyond a pilot project in following fiscal year. | Objective to be completed by June 30, 2013 | have purchased 5 streaming titles; 2 DVD to streaming and 3 born digital; work flows being tweaked.
Monograph Acq & P/C | Preservation/Conservation works with stakeholders to ensure that priorities for repair and conservation are being met and can be adjusted to respond to special projects or an unexpected increase in workload due to the acquisition of a collection or receipt of a gift. | Backlogs do not build. Quality of work does not decline. | Ongoing, adjusted as necessary in response to shifting priorities or incoming special projects. | Average monthly stats doubled during summer months as expected. Four student workers are assigned to an ongoing music material project and the average length for an item from this project to work through pres/con is 3-4 weeks. Since July 2012, 1417 items have been processed and 5916 treatments performed.
Music | Develop collection in the area of theory, composition, and musicology (TCM). | Number of items purchased; amount expended. | Firm order monies for this purpose expended by March 31, 2012. | Completed
Music | Process and catalog at least half of the Conrad Sharpe materials gift and the Thomas Moore materials gift collections. | Percent of each collection processed and cataloged. | June 30, 2013. | Sharpe collection completed. Moore collection completed.
Music | Inventory the entire collection of "Collected works". | Documentation of inventory. | June 30, 2013. | "Complete collected works" collection inventory finished. "Selected collected works" and "monuments to music" collections begun in June, 2013 and scheduled for completion in the new fiscal year (i.e., not intended to be completed in this fiscal year, though indicated as such in column E).
Music | Revise the Pepper Approval Plan and the Music Library's collection development guidelines. | Completion of Pepper Approval Plan revision; completion of collection development guidelines revision. | June 30, 2013. | Pepper approval plan revision completed. Collection development policy revision completed.
North Carolina Collection | Continue expansion of the Roberts Collection of North Carolina Fiction. | Documentation that retrospective (pre-2010) want list is reduced to less than 100 titles. | June 30, 2013. | Expenditure of grant funds began in September. Some $18750 in grant and matching funds were expended for the acquisition of over 1,150 volumes.
North Carolina Collection | Provide for proper storage of original Daily Reflector volumes. | Documentation that all original volumes are cleaned, wrapped, and relocated to NCC closed stacks. | December 31, 2012. | Storage sufficient for the project was arranged in the closed stacks of the NC Collection. 164 folio volumes were cleaned, wrapped and removed to the third floor.
Research and Instruction | Complete shift of Microfilm Collection. | Documentation shift completed. | August31, 2012. | Completed in August 2012. Minor shifts continue as needed for space.
TRC | Continue to promote the use of the educational component of the Eastern NC Digital Library, Daily Reflector Image Collection, and Ensuring Democracy through Digital Access to ECU pre-service teachers and eastern NC in-service teachers. Promote the integration and use of The Mini-Page digital archives to ECU pre-service teachers and eastern NC in-service teachers. | TRC Outreach Coordinator provides demonstrations using these digital collections at a scheduled meeting during summer 2012. Method developed to validate promotion of these collections during instructional sessions. Statistics on number of sessions in which digital collections are emphasized with goal being to include digital collection promotion in 75% of instructional sessions. | Statistics are collected throughout the year and analyzed in May 2013. | TRC Outreach Coordinator held training session to provide ways to promote digital collections via individual, small group and large group instruction in summer 2012. Method was developed to record statistics and validate promotion of these resources. Statistics are being collected through May 2013 and will be analyzed in June 2013. In addition, TRC Outreach Coordinator is promoting digital collections and archives via school faculty meetings and in eastern NC school classrooms.
University Archives and Records Management | Work with student government and Greek life advisors and representatives to develop plan to collect student life materials from student organizations. Meet with directors of Student Activities and Organizations and Greek Life and have written plan to expand collection of Student Associations and Organizations Records (item 318) and Student Government Association Records (item 321). Test plan in spring 2013. | Documentation of meetings with representatives and development of a written plan. | Meeting held and plan written by December 31, 2012. Plan tested in spring 2013. | Plan to improve collection of student life materials developed.
University Archives and Records Management | Develop plan to collect content from social media sites on university accounts as required by public records law. Implement plan with selected sites to test feasibility. | Written plan is developed and implementation tested with at least two specific sites (likely Joyner Library and the Honors College). | December 31, 2012. | Testing harvesting of social media site with Joyner Library and the Honors College. Considering possible harvesting tools that may make the process easier.

## 5
5. Improve accessibility and increase awareness and use of library collections, services and programs
Application Services and Design | Continue to identify new applications by monitoring trends and best practices as well as projects at other institutions. Specifically target applications which promote library collections in new and unique ways. Release and publicize new applications as developed. | Number of new applications identified; number of new applications developed, released, and publicized; user feedback; usage statistics/analytics. | June 30, 2014. | Room reservation, FAQ system; Die-cut search
Circulation/ILL | Publicize the holds, recalls, reserves, and cooperative borrowing services. Review the 2011 Faculty Survey, identify services with relatively low use, satisfaction or awareness and develop plan to increase awareness of and satisfaction with these services. Each semester create at least one plasma screen/website announcement and send at least one email message to the Announce list. Prepare sample announcements for library liaisons to consider including in their contacts with faculty by August 2012. Prepare a handout to distribute at new faculty orientation by August 2012. | Creation of plan; number of announcements created, emails sent, and handouts distributed. | Ongoing. | Approved Circulation staff have been trained to add slides to the plasma screen, with approval. New pamphlets were created to advertise improved Place Hold Service and Check out Equipment. A combined Circulation and Interlibrary Loan Brochure was created and is being used on display racks advertising.
Circulation | Provide a hands-on staff training session for each type of circulating equipment before the beginning of fall semester. | Number of sessions held. | August 17, 2012. | Two sessions were held with Circulation staff providing training with co-workers regarding different equipment they knew how to use.
Circulation | Migrate all paper forms, applications and other patron and departmental documents from print to online. | List of documents migrated from print to online. | Forms created and migrated online by June 30, 2013. | Some documents were moved so patrons could print copy and complete form before submitting to Circulation .
Circulation | Identify differences between Joyner and Laupus circulation guidelines and investigate options for consistency. | Documentation that comparison was made and discussions held. | Guidelines are compared and differences identified by Dec. 2012. Discussions to increase consistency are held with both libraries by June 2013. | Differences have been identified and initial conversation held with Assistant Director for Public Services to investigate. Policies were compared and differences identified in Dec. 2012. Discussions to increase consistency were held with both libraries in March 2013 and a new revised circulation policy was submitted to the OPRC Committee and was approved by Library Assembly in May 2013.
Collection Development | For uncataloged micro-format materials, deselect any sets not needed and prioritize remaining sets for cataloging. | List of prioritized sets delivered to cataloging. | July 31, 2012. | Review has been completed; list sent to cataloging.
Collection Development | Work with colleagues in Electronic & Continuing Resources Acquisitions to review un-tracked content represented in the Serials Solutions KnowledgeWorks that is freely accessible online; review this content to determine what should be activated; and then, on an ongoing basis, respond to their lists of newly-added freely accessible content to identify what to activate. | List of titles from ECRA is reviewed; response sent to ECRA in a timely fashion. | Response sent within 30 days of receiving the lists. | Developing a work flow; ongoing.
Collection Development | Analyze and respond to faculty survey by discipline, looking for appropriate opportunities to promote library collections and services. | Number of individual contacts across all CDV librarians increased by 10%; number of group contacts across all CDV librarians increased by 10%. | Outreach events conducted by June 30, 2013. | Number of individual contacts increased from 3 to 20; number of group contacts decreased from 21 to 18. However, attendance (covering both individual and group contacts) increased from 234 in 2011-21 to approximately 400 in 2012-13.
Collection Development | Monitor changes in university programs that result from the program prioritization, and recommend any necessary changes in liaison assignments. | Any needed changes reported to the Assistant Director for Collections and Technical Services. | June 30, 2013. | No further changes in Liaison assignments necessary at this time
Collection Development | Promote federal documents within the various subject areas. | Displays and/or promotional material developed in conjunction with the federal documents and social sciences librarian. | June 30, 2013. | The Cold War and Internal Security Collection (CWIS) was announced and its marketing campaign begun. Collection has already received interest from ECU faculty in Sociology and Music, as well as from colleagues at other institutions and was mentioned on the Facebook page of the Wilson Center’s Cold War International History Project in Washington, DC.
Discovery Committee | Continue to evaluate other databases for inclusion into the massive Summon index | Add one new "repository" to the Summon index in FY2013, possibly the North Carolina Periodicals Index or EAD finding aids. Consult with new Digital Archivist as to most appropriate collection(s) and process. | Multi-year goal; one new repository added to Summon in FY2013. | It is a personal goal of the Discovery Services Librarian for CY2013 to work with the Digital Archivist to ingest Joyner Library's EAD Finding Aids into the Summon Index.
Electronic & Continuing Resources Acquisitions | Develop and implement workflows for the monthly collection and library-wide distribution of data regarding e-resource use. | Workflows successfully developed and implemented | Implementation by September 2012. | Achieved.
Electronic & Continuing Resources Acquisitions | Continue to ensure that electronic resources within the library's collection are easily accessible from and accurately reflected within the library's database list, Summon instance, e-journal/e-book portal, link resolver, and other interfaces for electronic resource access and discovery. | Barring complications and inaccurate vendor information, access to newly acquired e-resource content is set-up within 3 working days of notification from the vendor that access is available. When problems are identified with e-resource access (e.g., linking problems and inaccurate coverage information), those problems are corrected and, when appropriate, steps are taken to identify related problems in access. Vendor notifications regarding changes in e-resource access are reviewed and appropriate measures are taken to reflect the changes in ECU access and discovery interfaces. (Formerly, the measure for this objective also included the following: "Review all database list description pages for accuracy and for effective linking and, when necessary, make updates." This was removed in April 2013 due to the fact that review of database list descriptions is instead being handled by the Discovery Committee.) | Ongoing as changes in electronic resource access are needed. (This timeline formerly indicated "Complete the database list review by June 30, 2013." This timeline was revised in April 2013 due to the fact that the Discovery Committee is now leading the database list review.) | This is an ongoing goal that is currently being met. Certain responsibilities for meeting this goal have shifted to the Discovery Committee. For example, the Discovery Committee led a project to redesign the database list and, as one part of that project, the committee considered approaches to revise/review/update database description pages.
Electronic & Continuing Resources Acquisitions | Promptly respond to and successfully resolve reports of problems accessing electronic resources. | During office hours, patrons submitting error reports receive an initial response from department personnel within 2 hours of the submission time. All error reports that are submitted are addressed and closed. In cases in which it is not possible (e.g., due to limitations in interface functionality or access rights) to resolve the concern/request submitted in an error report, the department will evaluate to determine what follow-up action is needed (e.g., submit interface enhancement request to vendor, suggest patron submit e-resources request form, etc.) | Ongoing, as error reports are received. | This is an ongoing goal that is currently being met.
Electronic & Continuing Resources Acquisitions | With colleagues at Laupus Health Sciences Library, complete work to enhance and redesign the functionalities and interfaces associated with submitting and tracking electronic resource error reports. | Input from library personnel, focus groups, and patrons. | Complete major work on enhancements and redesigns by August 17, 2012. | Achieved.
Electronic & Continuing Resources Acquisitions | With colleagues at Laupus Health Sciences Library, investigate the potential feasibility and benefits of the libraries migrating from separate website database lists to one shared database list. | Complete assessment, and if deemed feasible and beneficial, submit a recommendation to library administration to migrate to a shared database list. | Complete assessment and, if necessary, submit recommendations by April 30, 2013. | Responsibility for this goal has shifted to the Discovery Committee. This committee led a project to develop a shared Joyner-Laupus database list.
Electronic & Continuing Resources Acquisitions | Identify un-tracked content represented in the Serials Solutions KnowledgeWorks that is freely accessible online; in collaboration with colleagues with collection development responsibilities, review this content to determine what should be activated; and then, on an ongoing basis, identify and review freely accessible content that is newly added to KnowledgeWorks. | Initial review is completed and, based on the review, the content that is deemed acceptable is activated. | Initial review and activations completed by June 30, 2013. (Formerly, the timeline for this objective was by December 31, 2012. The timeline was revised in April 2013. | In progress. The department has completed an initial review of un-tracked freely accessible content in Serials Solutions KnowledgeWorks and it has also outlined workflows for identifying further content on an ongoing basis. The Collection Development Department is currently building on the ECRAD's initial review work and will communicate back to ECRAD regarding what content should be activated.
E-Resources Review Committee | Increase evaluative feedback from ECU Libraries' patrons regarding electronic resources under consideration by the committee. | An increase in the amount of evaluative feedback received (whether via online evaluation form, email, face to face, etc.); experiment with and, when deemed appropriate, broaden the methods by which evaluative feedback is solicited and received. | June 30, 2013. | Ongoing. The committee pursued conversations in order to brainstorm ideas to increase feedback regarding trialed resources. This is an objective for ERRC during the 2013-2014 cycle, and, during this period, the committee will work to implement some of the ideas that have been raised to increase the feedback.
General Collections Cataloging | Eliminate backlog of ILL POD ETDS. | ALL ILL POD ETDs are cataloged. | September 1, 2012. | Ongoing; 30 left to do; anticipated completion date 7/31/2013
General Collections Cataloging | Complete cataloging of all e-resources on the e-resources cataloging tracker | All e-resources on the tracker are cataloged. New sets of MARC records are edited and batch loaded into Symphony within 10 days (such sets often require special help from the Integrated Library System administrator). | E-resource on tracker are cataloged by December 31, 2012. Batch loading of new MARC sets is ongoing. | Not a static list but is current through the May 2013 updates
General Collections Cataloging | Catalog routine items for the general stacks, Reference, Music Library, Federal Documents, DVDs, and other materials, as needed, in a timely manner. | Holding department satisfaction; absence of a persistent backlog. | Ongoing; | Nothing backed up except gifts, which are low priority.
General Collections Cataloging | Retrospectively catalog government documents in selected subject areas as directed by the Federal Documents Librarian. | Selector's satisfaction. | Ongoing | All the Centers for Excellence, Education and Defense materials done; working on Energy now.
General Collections Cataloging | Resolve cataloging and physical processing problems with materials submitted by other departments in the library. | Absence of a persistent backlog. | Ongoing | No backlog at present.
General Collections Cataloging | Catalog large gift collection of DVDs/blu-rays. | All volumes are completed. | December 31, 2012. | Completed.
General Collections Cataloging | Begin cataloging microform sets based on prioritized list provided by Collection Development. | List in place, staff training completed. | February 1, 2013. | Have not started this yet due to staff member still working on a previous project.
General Collections Cataloging | Perform database maintenance projects in Symphony, as needed, to facilitate better discovery results for patrons. | Clickable access provided to all 26,300 + federal government documents with the current location Ask at Reference Desk. | Long-term project; originally projected completion October 2013, but project ahead of schedule; will be completed by December 31, 2012. | Ask at Ref project (electronic) is done; project to update Ask at Ref items for 18,000+ microform records has started.
General Collections Cataloging | Add barcodes and/or item records for all serial volumes in the general stacks that are not in Symphony. | All 10,000 volumes completed. | December 31, 2012. | Completed
General Collections Cataloging | Add barcodes and/or item records for all serial volumes in the North Carolina Collection that are not in Symphony. | All volumes are completed. | June 30, 2013. | Completed
ILL | Publicize ILL Borrowing, Purchase-on-Demand, and on-campus Document Delivery services through use of plasma screen and web site announcements and emails to the Announce list. Prepare sample announcements for library liaisons to consider including in their contacts with faculty by August 2012. Prepare a handout to distribute at new faculty orientation by August 2012. | Number of announcements and emails sent; creation of handouts. | Handouts created by August 2012; other publicity is ongoing. | A flyer was distributed at the 2012 new faculty orientation. A bookmark began to be distributed in August with purchase-on-demand titles to inform patrons that their requested title is being added to the library's collection. Announcements were included in the November and February library enewsletters. A shared brochure for Circulation and Interlibrary Loan was created in conjunction with library Marketing.
ILL | Collaborate with Circulation, Music, and Laupus Library Document Delivery to investigate efficiencies in the provision of ILL services. | Documentation of process and development of plans. | Meetings are held and plans developed by June 30, 2013. | A new courier service between Joyner and Laupus was begun that is speeding delivery of materials and reducing processing time. Joyner and Laupus merged our ILLiad databases during the spring semester; this will reduce annual license payments and server hosting fees, improve Laupus personnel management of ILLiad, and ease the registration and login processes for patrons. The Lanter courier service used by the ASERL/KUDZU consortium was joined in July 2012; the contract for 2013-2014 was cancelled after a review in spring 2013 found the service had failed to provide the cost and staff time savings, reliability, and speed compared to UPS. The use of new reusable book bands began in summer 2012. Lending expanded its fulfillment of requests with PDFs saved directly from databases, as allowed by licenses, and by scanning microform documents directly to PDF. The free OCLC Article Exchange service was implemented; this replaces the annual subscription-based Ariel delivery system and is easier to use. Circulation began checking ILL materials out to patrons in June 2013, which provides more accurate tracking and allows ILL staff to send emails quickly to patrons to remind them to pickup received materials. A new overhead scanner was purchased in May; it streamlines the scanning process and adds the ability for ILL to provide color scans. The summer 2013 renovation/combination of the Circulation and Interlibrary Loan office spaces, a retirement vacancy in ILL that will not be filled, and a determination that Circulation staff can take on additional ILL tasks are resulting in a complete review of all ILL processes. Additional research into other methods to improve ILL processing is on-going.
IT Operations | Deploy digital signs in Reference, TRC and Administration. Investigate other potential locations for digital signs. | Number of signs installed and operational. | December 31, 2012. | Signs have been deployed in RIS, TRC, and will be installed at the new Circulation desk. The new signage system, Xibo, has also been deployed by ASD. Appropriate staff have been trained to use this system to create announcements and promotional materials.
IT Operations | Increase the promotion and marketing of library spaces and technology to teaching faculty in the ITCS monthly Technology Digest, library e-newsletter, annual report, and library website. | Number of promotional pieces. | Ongoing. | Organizational changes have halted this goal for now.
IT Operations | Expand and continue collaborative efforts with the SOAD, College of Technology and Computer Science, and the Instructional Design program to promote and investigate teaching and learning technologies in the library. | Number of contacts and collaborations; usage by students and faculty. | June 30, 2013. | Organizational changes have halted this goal for now.
Manuscripts and Rare Books | Create LibGuides for HIST 3000, HIST 4000, and for primary sources in Manuscripts and Rare Books. | Number of LibGuides created; number of views. | LibGuides are created by October 1, 2012, and incorporated into library instruction sessions and into course materials for two classes in Blackboard as instructors request instruction sessions. Each LibGuide receives at least 100 page views by June 30, 2012. | Staff of the Special Collections Division worked with a faculty member in Research and Instructional Services, who developed a LibGuide that can be used for all classes taught by staff in the division. The LibGuide is available here: http://libguides.ecu.edu/specialcollections?hs=a. Between November 1, 2012, when the LibGuide went live, and June 30, 2013, the LibGuide had 318 page views.
Manuscripts and Rare Books | Link encoded descriptions of additions to manuscript collections to existing EAD finding aids for those collections. Link encoded finding aids for newly processed collections to the guides interface. | Number/percent of descriptions of additions linked to existing EAD finding aids; number/percent of encoded finding aids for newly processed collections linked to guides interface. | All encoded descriptions of additions to manuscript collections are linked to EAD finding aids by June 30, 2013. By June 30, 2013, all encoded finding aids for newly processed collections are made available through the guides interface. | All addition descriptions in Archivists’ Toolkit are currently available in the online finding aids. There are 28 collections that have various sections that are not up-to-date (missing additions, incomplete or lacking container lists, etc.). Two staff members will work together to ensure that these finding aids are updated in Archivists’ Toolkit and made available online.
Manuscripts and Rare Books | Contact professors to encourage them to make assignments requiring use of primary sources in the department and to hold instruction sessions in the library. | Number of professors contacted; number of sessions held. | By April 15, 2013, an instruction session is held for at least one new class. | Sessions were held for three new classes: HIST 3225, HIST 6155, and HNRS 3002.
Monographs Acq + P/C | Create a weekly post for the library's Facebook account that highlights recent, important or interesting monographs acquisitions that are available for patron use. | Four posts a month to library's unified social media presence (once established). | June 30, 2013. | This has not been attempted yet.
Music | Creatively utilize social media to highlight the music library's offerings and services. | The number of posts and interactions/comments/responses is recorded as benchmark for future assessment. | June 30, 2013. | Completed. Will be evaluated in the new fiscal year.
North Carolina Collection | Expand scope of the North Carolina Periodicals Index. | Documentation that indexing of five new titles has begun and five retrospective titles have been completed. | June 30, 2013. | All goals for expanding coverage of the index were exceeded. Several gaps in coverage were eliminated, the number of database entries grew by more than 3,000 this year.
North Carolina Collection | Continue improving accountability of serial volumes in the NC Collection. | Documentation that serial records for Reference, Oversized and closed stack materials are updated to include item numbers. | June 30, 2013. | The documentation of all sections of the collection is complete. Each bound volume or container has a item record in Symphony.
North Carolina Collection | Promote recent acquisitions to NC Collection. | Documentation that web page for new NC Collection materials is mounted by December 31, 2012; at least four notices on new materials appear in library and division newsletters by June 30, 2012. | See measures. | Collection web pages were migrated by September and updating continued for the remainder of the year. New approaches to regularly highlighting recent acquisitions are still being considered. Five articles appeared in Library newsletters or reports.
Research and instruction | Redesign LibGuides for updated content and standardized nomenclature. | Number of LibGuides redesigned to meet new criteria. | August 30, 2012. | Redesign of LibGuides was completed ahead of schedule and was ready at the beginning of class fall semester 2012. The new redesign features consolidated subject guides, a drop-down navigation system, and updated content. Styles are being coordinated with those of the Laupus Library and access to the LibGuides were included in the new Blackboard modules in spring 2013.
Special Collections Cataloging | Catalog items for Special Collections, NC Collection, TRC in a timely manner. | Holding department satisfaction. | Ongoing | Cataloged 1060 items for Special Collections, 1150 items for NC Collection, and 4300 items for TRC this year.
Special Collections Cataloging | Catalog items from the original (2010) Stuart Wright purchase. | 2400 of approximately 3500 items completed. | June 30, 2013. | Cataloged 914 items for the Stuart Wright Collection this year, bringing total 2010 purchase books cataloged to 1988.
Special Collections Cataloging | Catalog items for Digital Collections, exploring ways to reduce the size of the pending cataloging list | Pending cataloging list reduced in length. | June 30, 2013. | Cataloged 1587 items this year. 2105 items remain in progress. Increased Digital Collections output means that the size of the list has not been reduced, however, thanks to a temporary staff member we had for nine months, we have done well keeping pace with the work.
Special Collections Cataloging | Catalog items for Digital ECU history timeline collection in time for late summer advertisement | Items appearing on the timeline are cataloged. | August 31, 2012. | Completed on time.
Special Collections Cataloging | Examine new version of MODS schema and suggest changes to Digital Collections. | Changes suggested. | June 30, 2013. | Postponed.
Special Collections Cataloging | Clean up authority change-related errors in headings in Digital Collections database | Changes made. | Annually, by June 30, 2013. | Postponed. We are investigating options for automating such updates. Patricia heard about a possibility at the American Library Association Annual conference.
Special Collections Cataloging | Process each quarter's Backstage authorities reports in Symphony. | Reports processed. | Before the next quarter's reports are posted. | Changes are being made as problems are discovered. We are behind due to the extremely large size of reports during RDA changes. For example, the April notification load included 60,000 authority records and the January load included 20,000. Previous loads tended to average closer to 10,000. Larger loads lead to larger reports.
TRC | Actively promote TRC resources and services to the faculty and students of the College of Education in the instruction and curriculum areas of middle and secondary grades. | The plan developed to collect statistical data to indicate success of this goal is implemented for 2012-2013 and prepared for analysis. | TRC will review the subject area of Language Arts for strengths and weaknesses of middle/secondary materials by November 2012. | TRC Education Librarian devised a list of recommended titles (Grades 6-12) based upon strengths and weaknesses of the collection as well as the needs based upon the Common Core Standards. Funding was requested to purchase these materials in January 2013, but not granted. A request for end-of-the-year funds was requested in May 2013 to purchase the materials on this list which is still pending.
TRC | Explore and develop the integration of QR codes in TRC bibliographies and the TRC Easy Book collection. | Documentation of process and recommendations. | Explore and discover possible uses of QR Codes in TRC by Dec. 2012. | Possible uses of QR codes were explored. QR codes were assigned to ten Book Award Winner bibliographies and to the eleven most used TRC bibliographies in fall 2012. QR code project was promoted via Joyner e-newsletter, TRC Treasure Chest newsletter, instructional sessions and a poster advertisement. It was realized in the spring semester that the statistics were not being properly recorded for the usage of the individual QR codes. After consultation with Michael Tucker of Application and Discovery Services, we determined that the best way to offer the QR code was to provide one QR code for all of the bibliographies which would allow us to track usage internally. If significant use is realized, then QR codes will be added to individual bibliographies. It was decided that we would not pursue QR codes for books at this time.
TRC | Implement the training and use of the newly purchased Poster Maker System for the TRC ETC room. Develop procedures and guidelines to effectively incorporate this production item into the ETC room by Aug. 17, 2012. Begin promotion of this service in August 2012; promotion will be ongoing. Revisit procedures and guidelines to make any changes necessary by February 2013. | Procedures and guidelines are developed; usage statistics; documentation of promotional efforts. | Procedures and guidelines developed by Aug. 17, 2012. Promotion begins in August 2012 and is ongoing. Revisions made by February 2013. | Procedure and guidelines were developed by July 15, 2012. Service implemented in August. Promotion began in August and is ongoing via newsletters and instructional session announcements/orientations. Due to high volume of use, procedures and guidelines were reviewed in late August. Cost per poster was examined based on statistics. Price of each poster was increased in September 2012. Service was reviewed again in December 2012 with no revisions needed.
University Archives and Records Management | Complete 100 EAD finding aids for University Archives material. | Number completed and available online. | January 31, 2013. | More than 120 finding aids have been completed and half of those are now available online.
University Archives and Records Management | By December 31, 2012, meet with academic department representatives in at least 15 departments to discuss retention schedules, departmental record coordinators, electronic records, faculty papers, and use of University Archives materials. Depending on the results of those meetings (including the amount of work resulting from the meetings such as retention schedule updates, needs for record inventories, training needs), plan to meet with an equal number of departments in spring 2013. | Number of departments met with; documentation of results of meetings. | Initial round of meetings completed by December 31, 2012. | Met with 15 departments in fall 2012. Based on those meeting developed handouts and online content to assist records management users. Met with an additional 26 departments or offices before June 2013.
University Archives and Records Management | Digitize images related to campus sites and develop online map to provide access to digitized images and revised building histories in collaboration with Digital Collections and Application Services and Design. Develop tours of campus on specific historical topics. | Number of building histories updated, images identified, and amount of tour content developed. Number of items digitized. Development of map. Availability of tours online. | Building histories updated, images identified, and tour content developed by June 30, 2013. Map developed (with Application Services and Design) and images digitized (with Digital Collections) by December 31, 2013. Tours available online by June 30, 2014. | "Buildings Upon the Past," a collaboration with the ECU News Bureau, was completed by June 2013.
University Archives and Records Management | Work with Digital Collections to improve the new university history timeline to meet the needs of users browsing university history materials in digital collections as well as those seeking university history context. | Documentation of additional content, including new text and images for timeline. | Gather additional content including new text and images for timeline content by December 31, 2012 so that Digital Collections can complete improvements by June 2013. | New text written and additional images identified by end of 2012. Identifying problems with current content/images on timeline including incorrect identifiers and dates ongoing.

## 6
6. Provide the University community and residents of eastern North Carolina and beyond with educational resources and cultural opportunities that foster engagement and learning.
Exhibit Committee | Coordinate the spring School of Art and Design Faculty Exhibition. | Plus/Delta following the exhibition reception. | Art installed by February 1st. Reception date TBA. | Four faculty from the School of Art and Design exhibited works. The exhibit was on display February-May. A reception was held on February 20, 2013.
Exhibit Committee | Select and coordinate a summer exhibition. | Plus/Delta following the mounting of the exhibition. | Art installed by June 15th. Reception date TBA. | Linda Fox's "The Return" went on exhibit in mid June and is scheduled to be up through September 15th. A reception is scheduled for August 29th. A book to collect feedback on the exhibit is available on a pedestal adjacent to the exhibit.
Exhibit Committee | Coordinate the fall Graduate Student Art & Design Exhibition. | Plus/Delta following the exhibition reception. | Art installed by October 1st. Reception date TBA. | Joyner Library’s “5th Annual Graduate Student Art and Design Exhibition” was on display November– January. A reception was held on November 15, 2012.
Green Task Force | Plan Earth Day activities by January 31, 2012; complete activities during April 2013, including a special event and an article in the Joyner Library E-newsletter. | Number of activities planned and completed; publication of article in E-newsletter. | Activities planned by January 31, 2012; activities completed during April 2013. | completed. This year we had a Joyner Library lunch video and discussion on Fracking.
Green Task Force | Update the Green Task Force Facebook page and LibGuide to advertise Green Task Force events, relevant resources, and other "green" activities throughout 2012-2014. | Timeliness and relevancy of updates in relation to the events/activities being held. | Ongoing. | We have decided it would be best to coordinate announcements with the social media committee. As a result, we no longer use the Facebook or LibGuide. Green Committee events are posted on the general Joyner Library Facebook page and homepage.
ILL | Collaborate with the Teaching Resources Center to consider and implement methods to improve the Educator Card School service for K-12 schools in the region. | Documentation of discussions and publicity. | Discussions held with TRC personnel and others as needed to explore options by August 2012. Implement changes and launch publicity throughout the year. | Discussions with the representatives from the TRC and Circulation were held in August. A new webpage was created with explanations of the service. A new library procedure was drafted and a registration agreement and outreach email were being drafted. The project was postponed by ILL and the TRC to pursue other objectives and because ILL had two extended staff vacancies.
ILL | Promote awareness of ILL’s Lending service to regional community colleges. | Documentation of publicity; usage statistics; report. | Emails sent to institutions by September. Results are tracked and compiled into brief report by Dec. 2013. | This project was postponed until the spring semester due to other tasks. The project was then not pursued since ILL had two staff vacancies for five months and since expanding the Lending service would have increased expenses.
Monographs Acq + P/C | Continue to be a resource for Preservation/Conservation training by staff members of the department teaching sessions at conferences held within Joyner library. | Workshops are taught. | June 30, 2013. | Ongoing. There was a session at the Jan. 2013 TRC Librarian to Librarian Summit.
North Carolina Collection | Promote resources of the North Carolina Collection through three exhibits highlighting NC materials. | Number of exhibits. | June 30, 2013. | Three exhibits were mounted this fiscal year: The Burnside Expedition the Civil War in 1862 North Carolina; Inaugurations in North Carolina; and The Paleontology of Eastern North Carolina.
North Carolina Collection | Promote information resources for the state of North Carolina through online guides to cartographic and government information on North Carolina. | Number of online guides revised and mounted. | December 31, 2012. | New online guides to these subjects are still under preparation.
Research and Instruction | Change the name of Reference Services to Research and Instruction Services. | Website is updated; email signature lines are updated. | Name change completed by July 2012. | Department name changed officially on July 1, 2012. During fall 2012 semester updates were made to position titles, business cards, webpages, LibGuides, etc. Physical signage at service desk completed in May 2013.
SPA | Organize and host the 10th annual Joyner Library Paraprofessional Conference including pre-conference planning which entails budgeting, calls for proposals/keynote speaker, facility set-up, volunteers, sponsors, parking, session schedule, registration, catering, door prizes and promotion and post conference assessment/evaluation. | Observation, number of attendees, number of sessions, number of sponsors, attendee and presenter feedback through a post -conference survey and post-conference evaluations. | June 30, 2013. | The SPA has postponed the 10th conference until 2014. Due to the construction taking place in the library, scheduling of the ECU class calendar and the numerous vacancies that are in the Library this year, it did not seem feasible to continue to plan the conference. Some essential departments are short staffed and volunteers are not able to keep up with the demands of planning a large conference as well as helping in their departments.
TRC | Organize and host the 8th Annual Librarian to Librarian Networking Summit. | Number of attendees, number of sessions, number of sponsors, attendee and presenter feedback through evaluations. | Summit planning occurs over fall 2012. Event is successfully held in Feb. 2013. | Planning occurred during spring, summer and fall 2012 with the event being held on February 2, 2013. Thirty-three sessions were provided with more than 220 attendees. Planning for the 2014 Summit began in April 2014 with the date scheduled for February 8, 2014. A contract has been signed with Newbery Honor Award winner Sheila Turnage. Date for proposal calls has been determined along with tentative date for opening of registration. TRC is happy to announce that the 2013 Summit was self-supporting with no cost to the library, other than staff time.

## 7
7. Manage fiscal and human resources to allow Academic Library Services to grow and develop.
Administrative Services | Assess ALS faculty and staff satisfaction with services in the areas of business services, organizational development, project development, and marketing; develop a plan for improving services. | Assessment Method: Survey of ALS faculty and staff and review of service improvement plan by Dean’s Executive Committee. Criteria for Success: Response rate of at least 75% on survey and positive feedback on service improvement plan by Dean’s Executive Committee. | Develop, conduct, and assess the survey by November 1, 2012 and submit the service improvement plan to the Dean’s Executive Committee by May 1, 2013. | Decision was made not to administer a survey, partly because the SPA Assembly administered a staff survey this year. The results of that survey were analyzed and discussed at an SPA meeting and a Library Assembly meeting. The Climate Survey results were used to determine training/development needs. The Library Personnel Administrator arranged for three sessions to be offered twice by ECU HR. Attendance at least one of the sessions was mandatory. In addition, the interim dean gathered feedback about Administrative Services staff during her evaluation meetings with faculty this year and shared it with the department. Satisfaction levels were high. The need for prompt communication was reiterated.
Application Services and Design | Develop an intranet to better manage and access internal ALS information, documents, and records. Continue to weed files, configure SharePoint sites, provide training for library staff. | Number of SharePoint sites configured; library staff feedback on usability of SharePoint sites; use of sites by library staff. | Have SharePoint site configured for use by Fall 2012 and have new intranet used regularly by library staff by Jan. 2013. | A committee was formed in Jan. 2013 to further assess the needs of a library Intranet. A smaller working group was tasked to develop the Intranet and clean up the Pirate drive and its organization. That work is ongoing but should be completed by end of Summer 2013.
Discovery Services | Support single e-Library interface for Joyner and Laupus Libraries should it become a reality. Identify and implement features that mesh into the overall vision and plan for a joint OPAC for the ECU Libraries. Continue to document procedures, workflows, and customizations. | Documentation of enhancements and modifications implemented. For desired features not readily available, documentation of submission of enhancement requests to the vendor and/or identification of other means of accomplishing the desired feature. | Ongoing; documentation is current as of June 30, 2013. | The single e-Library OPAC for the ECU Libraries was completed in August of 2012. The Libraries assembled a task force of individuals with representation from both libraries. The task force was able to implement features to enhance the catalog interface and streamline shared services. A separate task force conducted an evaluation of e-Library indexing to determine if tweaking the index would result in better result relevancy. The determination of the group was that no further additions or retractions to the index would improve the effectiveness of the search. The Discovery Committee acted on this data to support a recommendation to investigate a suitable catalog replacement, specifically the VuFind discovery layer. The ILS Administrator documented workflows and processes throughout the process.
Business Operations | Improve service to internal and external clients through examination and possible reallocation of Business Operations staff job responsibilities. | Documentation of reassigned responsibilities; positive feedback from internal and external clients; improved turnaround time. | Examination completed by July 15, 2012; if reallocation of responsibilities is deemed desirable, it is completed and staff members receive necessary training by Sept. 30, 2012; transfer of responsibilities is effective no later than Oct. 1, 2012. | Completed: responsibility for travel was reassigned to Musselwhite effective July 1, 2012. Musselwhite attended two training sessions. Turnaround time has improved and feedback is positive.
Business Operations | Improve service by providing library borrowers the option to pay overdue circulation fines using credit cards through a U-Store application (collaborative effort with Application Services & Design and the Circulation Department). | U-Store application is operational with 100% accuracy on the financial processing component; U-Store application is integrated into the library website and is used by borrowers; positive feedback from borrowers. | Available on the library website for use by borrowers by August 15, 2012. | Investigated but have not completed due in part to the need for Circulation to complete the process of collecting old debts and then writing off uncollectible debts.
Circulation/ILL | Hold ILLiad cross-training for Circulation staff in order to better serve patrons on weekends. | Number of training sessions held; documentation of improved response time for ILL requests on weekends. | Training sessions are held for staff in both departments by June 30, 2013. | Input into desired topics for training of Circulation staff was sought in March and December. Follow-up training was provided to those who asked. Group training sessions have been postponed. Instructions are being prepared that will be able to be consulted. Two training sessions on answering patron questions about ILL were held for Circulation employees in March. Circulation staff did not begin processing requests on evenings or weekends.
Collection Development | Collection Development librarians will recommend changes in allocation methods to tailor support to their respective programs. | Document the balance of support for each subject area, to include firm order allocations, approval plan, and patron-driven acquisitions; report to library administration. | June 30, 2013. | Lisa and Cindy have constructed an alternative method, which was the subject of a presentation at Timberline (May 2013) and the basis of proposed FY2014 firm order funds.
Development Committee | Support the Advancement Council's goal of raising $150,000 by January 31, 2013, to fund the creation of the Janice Hardison Faulkner Gallery. | Amount of money raised. | January 1, 2013. | $120,000 received as of May 9, 2013, with approximately $12,000 in pledges and matching gifts outstanding. Development Committee drafted campaign materials (designed and produced by Wainwright) and letters to various categories of donors, managed the mailing of the letters, and sent thank you notes to donors. Development Committee promoted the Faulkner campaign through feature articles in area newspapers, blogs, social media, and targeted alumni with articles in EC Alumni and EAST magazines.
Development Committee | Research development programs in peer academic libraries and develop an advancement plan for enhancing ALS collections, resources, and spaces. | Positive feedback on plan from the Dean’s Executive Committee. | January 1, 2013. | Not completed; this was a personal goal of the former Assistant Director for Administrative Services.
Development Committee | Recruit at least two new members to the Advancement Council. | Number of new members who join the Council. | May 1, 2013. | Deferred until the new Development Officer is in place.
Discovery/Search Committee | Once Discovery Services Librarian joins ECU, work collaboratively with that individual to evaluate and revise goals and plans. | Discovery Services Librarian leads group, changes made as determined. | Dependent on hiring of Discovery Services Librarian [this librarian started July 16, 2012]. | This goal has been completed. Goals and objectives have been revised and updated. Leadership of the Discovery Committee has been condensed from a shared model, to the Discovery Services Librarian being the de facto chair working on behalf of the ECU Libraries.
Diversity Committee | Review and extend the ALS diversity plan to 2014. | Plan approved by Dean’s Executive Committee. | Complete by December 31, 2012. | Committee selected priority actions and submitted them for review by Dean's Executive Committee.
Diversity Committee | Improve diversity awareness: Partner with the Laupus Library Diversity Committee, Staff Development Committee, and ECU Office of Equity and Diversity to present the program Ouch! That Stereotype Hurts. | Positive feedback from attendees on program evaluation form. | Offer during the Fall 2012 semester. | This has been on hold pending selection of a date by the Associate Provost of Equity and Diversity. It is a priority to hold this program early in the next reporting period.
Diversity Committee | Assess organizational climate of diversity and inclusion with a survey of ALS faculty and staff. | 75% response rate on survey; analysis of survey results; results shared with Dean's Executive Committee. | Conduct survey during the Spring 2013 semester; analyze results and share results with Dean's Executive Committee by June 30, 2013. | Deferred until election of new committee members.
E-Resources Review Committee | Recommend acquisitions that will permit centralized electronic resources budgets to maximize access to needed content in the most fiscally prudent manner. | Electronic resource budgets are fully expended (but not over-expended) by the conclusion of the 2012/2013 fiscal cycle. | June 30, 2013. | Achieved. 6/28/13 materials budget spreadsheet shows that library materials budgets have been fully expended.
Electronic & Continuing Resources Acquisitions | Funds managed by the department are fully and appropriately expended within the 2012/2013 fiscal cycle. | Funds managed by the department are not significantly under or over-expended. Invoices processed by the department are accurately entered into the Symphony acquisitions module. There are no instances in which, due to department actions, resources were incorrectly paid from funds managed by the department. | June 30, 2013. | Achieved.
Electronic & Continuing Resources Acquisitions | Cross-train the ERAD Librarian position to better ensure for the continuity of department responsibilities and workflows. | The ERAD Librarian position is cross-trained regarding responsibilities for administrative workflows for subscription renewals, electronic resource licensing, set-up of electronic resource trial access, and administration of EZProxy. | June 30, 2013. | Achieved.
General Collections Cataloging | Migrate procedures and other internal documents to new departmental space on SharePoint, and explore SharePoint as a venue for departmental cooperation. | Procedure documents updated and migrated. | June 30, 2013. | This has been delayed by a decision to change from using LibGuides to developing a wiki.
General Collections Cataloging | Determine appropriate benchmarks and develop a more cohesive means of collecting and collating meaningful statistics that support them to reduce staff time spent on this task. | Establish viability of Symphony to generate at least some meaningful cataloging statistics and implement accordingly. | December 31, 2013. | This is now a joint goal with ILS for fiscal 2014
Manuscripts and Rare Books | Complete implementation of Archivists’ Toolkit as a content management tool. | Documentation of implementation. | By October 1, 2012, establish procedures and workflow for producing reports for acquisitions, thus precluding the necessity of producing acquisitions worksheets. By December 31, establish procedures and workflow for converting EAD finding aids as generated by Archivists’ Toolkit to conform with the department’s current style. | The reports created in Archivists’ Toolkit are basic and do not meet our needs. In order to produce reports that could replace the creation of acquisition worksheets, it will be necessary to use third-party software. The Digital Archivist has done preliminary research on iReport, and we will continue to work towards this goal during the first part of 2013. The Digital Archivist is in the process of creating documentation that explains the procedures and workflow for creating EAD finding aids in Archivists’ Toolkit. This documentation should be completed during the Spring semester. Update: After looking at the iReport (third-party software) it was determined that investigation of this program will take more time. Investigation of this program will continue and the workflow manual will be completed by the 2013 fall semester.
Manuscripts and Rare Books | In cooperation with IT Operations, form a committee to study how best to implement a GREEN initiative to move away from selling paper copies of documents in Special Collection. This would involve strategies such as self-serve image scanning systems such as the BookEdge, Bookeye, Flip-pal systems, and an existing public scanner; as well as the in-house use of patron hand held cameras and telephone camera devices. The goal would be to end our current practice of primarily providing paper copies which the patron then has to pay postage to receive. This initiative would reduce not only our copying costs, but also the labor involved. We would not stop making paper copies, but instead would encourage patrons, through our reproduction request pages, both in-house and off-site to use digital rather than traditional paper reproductions. This would reduce costs both for us and for the patron (scans are currently sold for $9.00 each). | Documentation of the study and recommendation. | By April 1, 2013, committee makes a recommendation on how to implement this initiative, including needed equipment purchase. | As of February 15, 2013, the committee has developed a revised form for requesting copies and scans; this will be made live on the Manuscripts and Rare Books Department's Web site as soon as the Digital Collections Unit makes a decision on the cost of scans. The committee agreed to order a digital camera for use by patrons. Update: The online form has been completed by IT and we are waiting to hear back from them. The form will be online by the 2013 fall semester. The self-serve image scanning products proved to not be practical in our research setting. The purchase of a digital camera for patrons to use will be further discussed and a decision made by the 2013 fall semester.
Monograph Acq & P/C | Cooperate with Collection Development to ensure that the monographs acquisitions structure correctly addresses the teaching and research needs of the campus community, including but not limited to allocation adjustments and adapting staff workflow in response to new acquisitions models or priorities. | Adjustments as necessary are made and documented. | June 30, 2013. | Analysis of workflows will be needed as various DDA programs leave pilot status
Special Collections Cataloging | Migrate procedures and other internal documents to new departmental space on SharePoint, and explore SharePoint as a venue for departmental cooperation. | Procedure documents updated and migrated. | June 30, 2013. | Delayed due to departure of web librarian, SharePoint delays. Had settled on LibGuides, but then the division decided not to go that route. Developing wiki instead.
Special Collections Cataloging | Recruit, hire, and train an SPA staff member to fill a vacancy in the Metadata Technician position. | Staff member hired and trained. | June 30, 2013. | Completed on time.
Teaching Resources Center | Explore the need for an additional TRC faculty member with job responsibilities focusing on specialized TRC instruction to better accommodate requests by faculty. Review library instruction statistics to consider increases in number of sessions, projected increases from Goal 3, increase in LibGuide requests as well as other technological integrations being used by public schools by January 2013. Analyze need for additional TRC faculty member in March 2013. Develop proposal to discuss with AD for Public Services in April 2013. | Statistical comparison; development of proposal. | April 30, 2013. | Discussion was held with AD of Public Services on need for an additional faculty member for the TRC to meet the demand for increase instructional requests for online instruction (Oct 2012). Administration approved the hiring of a temporary instructor to be shared between RIS and TRC. Justification was submitted to Interim Dean for approval by campus administration. Approval was granted. Job description and ad was written and submitted to ECU HR. Job was posted in late Mar 2013. Selection made in Apr. Candidate selected and started on May 1st, 2013 with contract through Oct 15, 2013.
University Archives and Records Management | Implement new database for records management. Begin implementing barcoding in the records center. | Documentation that all new accessions, records from departments with high retrieval levels, and records stored off-site are in the new database. Documentation that the stacks in the record center and records in the database are barcoded. | June 30, 2013. | New database acquired and installed by February 2013. By June 30, 2013 one-third of historical records had been transferred to new database.

## 8
8. Enhance the culture of leadership and participation within Academic Library Services.
Administrative Services | Member of the department serve on ALS committees and task forces. | Assessment Method: Feedback from committee/task force chair. Criteria for Success: Appointment to at least one ALS committee or task force and positive feedback from chair regarding participation. | Service on committee/task force to begin during Fall 2012 semester. | Wainwright served on the Development and Diversity Committees and the Dean's Council. She chaired the Publications & Marketing Committee. Sweatte served on the Diversity and Staff Development Committees and the Disaster Response Team. Tennent chaired the Eastern North Carolina Literary Homecoming Committee and served on the Development Committee and Dean's Council. Morgan served on the Marie & James Thompson Scholarship Committee, the Internship Committee, and the ECU Staff Senate. Rook served on the Disaster Preparedness Committee and the Disaster Response Team.
Application Services and Design | Lead the exploration and adoption of innovative technologies and services by monitoring trends and best practices in library/information technology and services, making recommendations for the adoption of technologies to benefit patrons and staff, efficiently implementing new technologies and services, and providing guidance in the evaluation of emerging and innovative technologies for other departments and divisions. | Number and description of new technologies or services that would benefit the library that are identified and implemented; feedback from faculty and staff on the effectiveness of the guidance provided for the exploration and adoption of new technologies by divisions throughout the library. | June 30, 2014. | Room reservation system; FAQ system; Die-cut search; Database List; ECU Libraries page. A custom results ‘bento’ search is under development, as is the VuFind discovery layer which is intended to be a catalog replacement.
General Collections Cataloging | Each member of the department will participate in at least one of the following, and report it in his/her monthly report: duty-related webinars, classes or conferences, library committees, library or campus events, public service. | Participation happens and is reported. | Ongoing. | Staff have participated in Staff Development Day activities and/or HR sessions on Understanding Career Banding, Effective Communication Skills, Building Trust and Teamwork
Green Task Force | Encourage faculty and staff to participate in sustainable efforts by planning a GTF Open House by November 2012 and one special event by May 2013 | Number of faculty and staff who participate. | Open House held by Nov. 30, 2012; special event held by May 31, 2013. | We did not have an Open House, but we did organize a faculty/staff event for Earth Day (movie event). We also collected corks and clothes from faculty/staff during the year.
IT Operations | Identify and participate in appropriate technology workshops to improve ALS skills in and awareness of technology. | Number of workshops identified; number of people who participate. | Ongoing. | A show and tell demo for upcoming Lenovo products was held in January 2013.
IT Operations | Lead the library in awareness of current technology trends, products and services, and seek to actively disseminate information and engage ALS in technology issues and discussions. | Documentation in annual report. | Ongoing. | Library Technology personnel have been pivotal participants in planning for new projects in Joyner Library, including OFE and classroom construction.
Monographs Acq + P/C | Each member of the department shall be encouraged to serve on a committee, if interested, or will attend at least one professional development or personal interest event held in the library. This may be in the form of a webinar, class, forum, speaker, presentation, facultea or similar. | Participation is reported. | November 2012 and May 2013. | Most staff are participating in something.
Special Collections Cataloging | Each member of the department will participate in at least one of the following, and report it in his/her monthly report: duty-related webinars, classes or conferences, library committees, library or campus events, public service. | Participation happens and is reported | Ongoing. | Completed as designed. Members of the department have attended: ECU HR training on Career Banding, Teambuilding, and Effective Communication; Library Forum on the Stuart Wright Collection by Professor Tom Douglass; Webinars on Emerging Cloud Technologies in the Library, reader’s advisory, LC classification and genre terms, digital preservation, OCLC RDA policy, transitioning from cataloging to creating metadata, rare materials and RDA; In-house training Mysteries of LC classification revealed! Special Collections exhibit opening; WordPress blogging class through ECU technology training; Online RDA training from the Library of Congress; American Library Association Annual Conference, Chicago, IL. One member of the department works regularly at the Special Collections service desk, and another worked regularly, until her retirement, at the Teaching Resources desk.
SPA | Provide leadership opportunities to staff through activities including the 2013 Paraprofessional Conference which offers a variety of leadership and professional development seminars, and through civic and philanthropic activities including fundraisers for charitable organizations (one held each semester) and the annual roadside cleanup event. | Number of sessions at the Paraprofessional conference; number of attendees; percent of staff who participate; feedback from attendees. Number of seminars; percent of staff who participate. Number of fundraisers and other events; percent of staff who participate. | June 30, 2013. | Roadside cleanup Fall: Complete, Charitable fundraiser and donation of $450.00 completed. Staff completed a Climate Survey that included more than 70% of Staff participation. Staff has meet with Consultants and there has been an increased participation in Library interests. Funding from Friends has provided numerous Staff members with development opportunities.
Staff Development Committee | Sponsor leadership centered sessions. | A minimum of three leadership sessions will be held during the academic year. | June 30, 2013. | Did not accomplish.
Staff Development Committee | Collaborate with Joyner Library's Diversity Committee to sponsor diversity-centered sessions. | A minimum of two diversity sessions will be held during the academic year. | June 30, 2013. | Did not accomplish.

## 9
9. Engage in campus and external collaborations to expand access to collections, improve services, share expertise, and advance the profession.
Application Services and Design | Create ECU History webpage for university. Research similar projects at other institutions, collaborate with Joyner faculty and staff and University Historian. | ECU History webpage is created by Jan. 2013. Digital Collections material is incorporated into webpage for increased publicity of collections. | January 30, 2013. | Completed
Application Services and Design | Participate in Digital Scholarship Pilot Study. Provide programming expertise and contribute to project management. Explore new opportunities for collaboration with ECU faculty. | Completion of work on Digital Donne and GIS projects; continuation of support for these projects; identification of additional projects for consideration. | June 30, 2013. | Digital Donne never materialized. A web mockup was created for the Coastal Atlas project (GIS), continued web support planned for after Geography Dept. server purchase.
Application Services and Design | Identify areas of potential collaboration between Joyner and Laupus Libraries, develop a more streamlined ECU Libraries brand, and create new, shared webpages. | Creation of a new ECU Libraries landing page, incorporating new, shared search widget. | December 31, 2012. | The ECU Libraries page has been redesigned. A new Database List has been developed. In addition to this were a variety of auxiliary pages that migrated to the new design to complement these new applications. A custom results ‘bento’ search is under development as is the VuFind discovery layer which is intended to be a catalog replacement for the libraries.
Circulation | Renew formal library service agreements with various libraries and consortia. | Formal letters and agreements are sent to each library director at the beginning of the academic year. | September 30, 2012. | All except two libraries updated their cooperative agreements.
Collection Development | Participate in ASERL collaborative programs on an as-needed basis, including the Collaborative Federal Documents Program, the Journal Retention Project, and any discussion related to a shared print monograph repository. | Narrative describing activities in the department's annual report. | June 30, 2013. | Ongoing. We have confirmed title list for J-Retain and are researching titles to add. We will need to add info to the MARC records of retained titles. GovDocs COE's have been enhanced by claiming titles other libraries have withdrawn.
Collection Development | Collaborate with Laupus Library Collection Development to make both libraries' collection development guidelines findable on both libraries' websites. | Links to Laupus Library's collection development guidelines appear on Joyner collection development pages; links to Joyner Library's collection development guidelines appear on Laupus Library pages. | November 30, 2012. | Has not happened. Reevaluate during joint strategic planning.
Discovery Services | Support the joint ILS implementation for Academic Library Services, Laupus Health Sciences Library, and ECSU's G.R. Little Library by implementing features, resolving problems and providing training. Visit Laupus & Little Libraries 2-3 times during 2012-2013 to identify areas that need assistance and provide the appropriate training. Coordinate efforts between the libraries where overlaps exist and negotiate agreements where necessary. | Number of training sessions are scheduled and conducted; completion of joint implementations/projects on project-designated timeline. | Training sessions are scheduled and conducted by June 30, 2013. project timelines are met. | Work that was begun in February 2012 to create a single OPAC interface for the ECU Libraries was completed and delivered in August 2012. Follow-up e-mails and phone calls occurred between ECSU library staff members and their Joyner counterparts throughout the year after newly hired ECSU staff visited Joyner Library in February 2012 for a meet and greet/Q&A day. ILS/Discovery Services staff visited and worked with Laupus staff in August 2012 to configure and facilitate Demand Management (holds) functionality. Two visits to ECSU were made in September 2012 to begin the discussion for configuring the system to include ECSU’s new music library branch. Two visits by ECSU music library, technical services, and circulation personnel to Joyner Library, including its Music Library branch, were made in October 2012 and January 2013 to continue discussions concerning music library and binding/preservation best practices. A visit was made by ILS/Discovery Services staff in January 2013 to continue the music library configuration in the ILS.
Electronic & Continuing Resources Acquisitions | Develop a presentation open to the entire library (perhaps as a Library Forum) regarding challenges of managing electronic resource access and opportunities for better promoting this access. | Presentation developed, announced to the library, and successfully given. | December 31, 2012. | Due to the need to meet higher priorities, this objective was not met.
General Collections Cataloging | Collaborate with Laupus and ECSU technical services personnel on RDA training and implementation. | Staff trained and RDA implementation plan in place. | June 30, 2013. | Elected to take a wait and see approach, since there has been rapid change in the RDA standard; will train staff as it becomes apparent what best practice for application might be.
General Collections Cataloging | Participate in discussions regarding the future of the ILS and discovery services in the library. | Discussions participated in. | As opportunities arise, by June 30, 2013. | Completed for now.
Green Task Force | Identify "green" library committees in North Carolina to collaborate or share ideas and information by May 2013. |  | May 2013. | Ongoing.
Green Task Force | Collaborate with other departments or committees across campus to encourage sustainable practices and/or recycling. This objective is a multi-year objective (2012-2014) with one activity to be planned by May 2013 |  | May 2013. | A number of committee members attended the Sustainability Committee meeting. We plan on being more involved with the larger ECU committee in the future.
ILL | Evaluate existing resource sharing partnerships and explore if different groups or reciprocal agreements are warranted. | Documentation of evaluative process. | Partnerships are evaluated by June 30, 2013. | The 43-member ASERL consortium, of which Joyner Library is a member, partnered with the eight-library WRLC Washington, DC area consortium to provided free, preferential lending services between all 51 members. The review of other consortial memberships was postponed when two staff vacancies went unfilled for five months; the review began again in June 2013 and will result in adjustments in 2013-14 to Lending billing categories and Borrowing custom holdings groups, which should improve Borrowing speed and reduce costs.
Monograph Acq & P/C | Explore avenues for increased cooperation between acquisitions and preservation/conservation units of Joyner and Laupus Libraries as a result of the PPC report. | Cooperation as necessary. | June 30, 2013. | Lisa has worked with Michelle at Laupus on acquisitions workflows in Symphony; Pres/Con cooperation is not as well-developed at this point.
Monograph Acq & P/C | Monitor ULAC and Carolina Consortium discussions/proposals which might affect monographs purchasing and access. Examples include but are not limited to: a ULAC library with an Espresso machine serving as a Print-on-Demand supplier for other schools; a consortia e-book DDA purchasing model; ASERL print monographs repository. | Participation where feasible, library administration is kept informed of important developments in these areas. | June 30, 2013. | Monitor ULAC study of collaborative e-book purchasing and contribute as possible.
Research and Instruction | Develop and teach 2 credit -hour course, Honors College Research Colloquium. Also, revise, market, and provide instruction for the Honors College Freshman Colloquium. Students will be assessed using a variety of methods to measure mastery of learning outcomes for each class. | Student learning outcomes. | Develop course by August 2012. Revise, market, provide instruction and assess by December 30, 2012. | Coonin and Whitehurst taught the HRNS Research Colloquium during fall 2012 semester including the creation of syllabus, devising of content, instructional methods and assessment of students through the use of weekly quizzes, group project, and final exam. Willis met with Dr. Fraley and Honors Freshman Coordinator; they revised the library instruction session for this group during fall as well. Instruction and tours were divided into different sessions and some information was taught outside of the library to accommodate the large class size. All completed by December 2012.
Research and Instruction | Collaborate with faculty from School of Hospitality Leadership and Laupus Library to conduct a literature review and devise an information literacy module to include in online learning objects developed for a BB&T Leadership grant-funded course. | Literature review completed; information literacy module developed; assessment documented. | Literature review and module will be completed by August 30, 2012. Assessment, analysis, and any revisions are completed by June 30, 2013. | Both library components of this project have been completed. The literature review was conducted by a library graduate assistant and completed by May 2012. Sanders, Whitehurst, and Kavanagh were engaged in the planning process and Kavanagh created both and introductory and advanced tutorial of library resources for the classes involved in the BB&T leadership grant. Library tutorial went live in August 2012 and entire grant project completed in December 2012.
Scholarly Communications | Engage with Faculty Senate Libraries committee to establish ways to work together. | Describe any coordinated actions, meetings, and/or programs in the 2012-2013 annual report. | June 30, 2013. | Chair of the Senate Libraries Committee has become an engaged member of the Scholarly Communication Committee, and has been helpful in promoting events.
Scholarly Communications | Evaluate NCDOCKS and recommend to library administration whether to continue current level of involvement, stop participating, or change our type of participation. | Recommendation to administrations of Joyner and Laupus Libraries. | September 30, 2012. | Recommendation not to increase our involvement with NCDOCKS for the institutional repository. However, we remain involved with NCDOCKS in a new venture: a data repository contracted with the Odum Institute at UNC Chapel Hill.
Scholarly Communications | Make contact with other potential partner units on campus, for instance those responsible for REDCap, Sedona, Open Journal Systems, and/or Academic Analytics |  | June 30, 2013. | Have been in touch with colleagues at the Division of Research and Graduate Studies (RGS) and Biwu Yang, who works with the OJS software. The RGS contact relates to a new project called "Research Roadmap," which should strengthen library relationships with that unit and lead to increased collaboration in research and data management. Although WJT has a REDCap account, he has not yet been able to contact the persons in ITCS and Brody who might facilitate library engagement. The temp SPA (Justin) has been working on OJS customization for an upgrade to the JOCI journal and adding backfiles for EDGJ.
Special Collections Cataloging | Collaborate with Laupus and ECSU technical services personnel on RDA training and implementation. | Staff trained and RDA implementation plan in place. | June 30, 2013. | Elected gradual implementation over the course of 2013-2014 as many libraries did. Waiting a bit longer has allowed best practices to develop, making implementation easier than if we were on the leading edge.
Special Collections Cataloging | Contribute NACO records to national program, drawing especially from manuscript collection creator names. | 100 NACO records contributed. | June 30, 2013. | No records were contributed this year, due to vacancy/training in the Metadata Technician position, and also in anticipation of RDA day one for NACO authorities on March 31, 2013. We completed the required NACO RDA training from December through March, consisting of approximately 20 hours of webinars and exercises.
Special Collections Cataloging | Collaborate with new Digital Archivist on exploring continuation of EAC project. | Possibilities explored, possible pilot begun. | June 30, 2013. | Postponed.
Special Collections Cataloging | Participate in discussions regarding the future of the ILS and discovery services in the library. | Discussions participated in. | As opportunities arise, by June 30, 2013. | Completed on time.
University Archives and Records Management | Work with Project Development to identify and apply for grant to digitize audio reels of music school performances. Work with faculty member from music school to identify reels appropriate for project. | Documentation that audio reels have been identified and grant application is complete. | June 30, 2013. | Possible audio reels for inclusion in the project have been identified and samples are being tested for condition and quality of digitization.